{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["WBS Thermostat Connecté"],"read":"whole","date_system":"1900"}

{"sheet":"WBS Thermostat Connecté","index":0,"n_rows":18,"n_cols":5,"rows_kept":18}
["Code WBS","Intitulé","Niveau","Responsable","Livrable attendu"]
["1.0","Projet : Thermostat Connecté","Niveau 1","Chef de Projet","Produit global livré"]
["1.1","Spécifications Produit","Niveau 2","Chef produit","Document de specs validé"]
["1.2","Développement technique","Niveau 2","Responsable R&D","Modules hardware et firmware"]
["1.2.1","Conception PCB","Niveau 3","Équipe Hardware","Schémas électroniques"]
["1.2.2","Développement firmware","Niveau 3","Équipe Software","Code embarqué"]
["1.2.3","Intégration des capteurs","Niveau 3","Tech capteurs","Module capteurs intégré"]
["1.2.4","Revue technique","Niveau 3","Chef produit","Validation fonctionnelle"]
["1.3","Design industriel","Niveau 2","Designer produit","Maquette physique + fichiers 3D"]
["1.4","Prototypage","Niveau 2","Ingénieur proto","Prototype fonctionnel"]
["1.5","Tests et certifications","Niveau 2","Resp. qualité","Conformité CE"]
["1.5.1","Tests électriques","Niveau 3","Bureau test A","Rapport de test électrique"]
["1.5.2","Tests radio (Wi-Fi, BT)","Niveau 3","Bureau test B","Rapport de test RF"]
["1.5.3","Certification CE","Niveau 3","Resp. qualité","Dossier CE"]
["1.5.4","Rapport de conformité","Niveau 3","Chef de Projet","Document consolidé"]
["1.6","Production pilote","Niveau 2","Resp. fabrication","Série test fabriquée"]
["1.7","Lancement marché","Niveau 2","Dir. marketing","Kit communication + packaging"]
["1.8","Support & documentation","Niveau 2","Service client","Guides et FAQ"]