## CAPA Log
➡️ CAPA Tracker — Corrective & Preventive Actions (CAPA)
ID CAPA | Type | Date de Signalement | Source | Processus / Zone | Titre | Cause Racine (Lien 5-Why) | Responsable | Statut | Date d'Échéance | Jours Restants | En Retard ? | Priorité | Sévérité (1-10) | Occurrence (1-10) | Détection (1-10) | IPR | Action Corrective | Action Préventive | Date de Vérification | Efficacité | Commentaires | Progression %
CAPA-100 | Corrective | 2025-08-05 | Audit | Area A | Leak detected on line A | http://example.com/5why/CAPA-100 | Ahmed | Open | 2025-08-15 |  |  | High | 1 | 4 | 7 |  | Immediate containment + root cause correction | Procedure update & training refresh
CAPA-101 | Preventive | 2025-08-06 | Customer Complaint | Area B | Training gap in forklift usage | http://example.com/5why/CAPA-101 | Fatima | In Progress | 2025-08-16 |  |  | Medium | 2 | 5 | 8 |  | Immediate containment + root cause correction | Procedure update & training refresh
CAPA-102 | Corrective | 2025-08-07 | Nonconformity | Area C | Late delivery root-cause | http://example.com/5why/CAPA-102 | Youssef | Implemented | 2025-08-17 |  |  | Low | 3 | 6 | 9 |  | Immediate containment + root cause correction | Procedure update & training refresh
CAPA-103 | Preventive | 2025-08-08 | Incident | Area D | Nonconforming batch B7 | http://example.com/5why/CAPA-103 | Sofia | Verified | 2025-08-18 |  |  | High | 4 | 7 | 10 |  | Immediate containment + root cause correction | Procedure update & training refresh
CAPA-104 | Corrective | 2025-08-09 | KPI Deviation | Area E | Safety signage missing | http://example.com/5why/CAPA-104 | Khalid | Closed | 2025-08-19 |  |  | Medium | 5 | 8 | 1 |  | Immediate containment + root cause correction | Procedure update & training refresh
CAPA-105 | Preventive | 2025-08-10 | Risk Assessment | Area A | Calibration schedule overdue | http://example.com/5why/CAPA-105 | Omar | Cancelled | 2025-08-20 |  |  | Low | 6 | 9 | 2 |  | Immediate containment + root cause correction | Procedure update & training refresh
CAPA-106 | Corrective | 2025-08-11 | Audit | Area B | Incorrect labeling on box C | http://example.com/5why/CAPA-106 | Nadia | Open | 2025-08-21 |  |  | High | 7 | 10 | 3 |  | Immediate containment + root cause correction | Procedure update & training refresh
CAPA-107 | Preventive | 2025-08-12 | Customer Complaint | Area C | Alarm not triggered in test | http://example.com/5why/CAPA-107 | Hicham | In Progress | 2025-08-22 |  |  | Medium | 8 | 1 | 4 |  | Immediate containment + root cause correction | Procedure update & training refresh
CAPA-108 | Corrective | 2025-08-13 | Nonconformity | Area D | Procedure not updated | http://example.com/5why/CAPA-108 | Leila | Implemented | 2025-08-23 |  |  | Low | 9 | 2 | 5 |  | Immediate containment + root cause correction | Procedure update & training refresh
CAPA-109 | Preventive | 2025-08-14 | Incident | Area E | High scrap rate on press D | http://example.com/5why/CAPA-109 | Amine | Verified | 2025-08-24 |  |  | High | 10 | 3 | 6 |  | Immediate containment + root cause correction | Procedure update & training refresh
CAPA-110 | Corrective | 2025-08-15 | KPI Deviation | Area A | Supplier defect recurrence | http://example.com/5why/CAPA-110 | Rachid | Closed | 2025-08-25 |  |  | Medium | 1 | 4 | 7 |  | Immediate containment + root cause correction | Procedure update & training refresh
CAPA-111 | Preventive | 2025-08-16 | Risk Assessment | Area B | Incorrect PPE usage | http://example.com/5why/CAPA-111 | Sara | Cancelled | 2025-08-26 |  |  | Low | 2 | 5 | 8 |  | Immediate containment + root cause correction | Procedure update & training refresh
Formulas:
Jours Restants = DATEDIF(TODAY(), [Date d'Échéance], "d")

## Lists (hidden)
Status | Priority | Type | Effectiveness | Source
Open | High | Corrective | Effective | Audit
In Progress | Medium | Preventive | Partially Effective | Customer Complaint
Implemented | Low |  | Not Effective | Nonconformity
Verified |  |  | Pending | Incident
Closed |  |  |  | KPI Deviation
Cancelled |  |  |  | Risk Assessment

## Dashboard
|  |  |  | Retard par Responsable | Nombre | Taux d'Achèvement | Nombre
|  |  |  | Responsable | Nombre en Retard | Clôturées | Non Clôturées
Ahmed
|  |  |  | Fatima |  | Nonconformity
|  |  |  | Youssef |  | Risk Assessment
|  |  |  | Sofia |  | Audit
|  |  |  | Khalid |  | Incident
Omar
Nadia
Répartition par Statut | Nombre | Répartition par Priorité | Nombre | Hicham
Open |  | High |  | Leila
In Progress |  | Medium |  | Amine
Implemented |  | Low |  | Rachid
Verified |  |  |  | Sara |  | Échéances Prochaines | Count (not Closed)
Clôturées | [5 empty] | Échéance ≤ 7 jours
Cancelled | [5 empty] | Échéance ≤ 14 jours
Calibration schedule overdue | [5 empty] | Échéance ≤ 30 jours
Incorrect labeling on box C
Alarm not triggered in test
Procedure not updated
High scrap rate on press D
Supplier defect recurrence
Incorrect PPE usage
Formulas:
Nombre = COUNTIFS(CAPALog[Due Date],">="&TODAY(), CAPALog[Due Date],"<="&TODAY()+7, CAPALog[Status],"<>Closed")