## README_Mode_Emploi
MODE D'EMPLOI — Modèle Excel Complet de Gestion des Risques (ERM) — Version Automatisée Parcours recommandé : 1) Paramétrez vos seuils dans 'Risk_Appetite' (Low/Medium/High/Critical). 2) Renseignez/complétez le 'Risk_Register' (préfilié) pour vos risques. 3) Déclarez vos 'Controls_Library' (préfiliée) et liez-les aux risques. 4) Définissez vos actions dans 'Action_Plan' (préfiliée) et suivez leur avancement. 5) Visualisez la matrice 5x5 (inhérente & résiduelle) dans 'Risk_Matrix'. 6) Pilotez via 'Dashboard' (KPIs, répartitions, alertes, échéances < 7 jours). 7) Consultez 'Flux_Risque' pour la descendance des flux du processus ERM. Automatisations ajoutées : - Codes risque auto (R-0001…), âge du risque (jours), prochaine revue automatique selon vélocité, jours restants avant revue, drapeau d'escalade (Residual High/Critical et action non Close). - Actions : statut de santé (On Track / At Risk / Late), surlignage couleurs et indicateurs KPI (Due in 7 days). - Dashboard enrichi (Due next 7 days, moyenne du score résiduel, distribution par vélocité). Notes : formules en anglais pour compatibilité Excel internationale (IF, COUNTIF, COUNTIFS, TODAY, AVERAGEIF).

## Risk_Appetite
Risk Appetite — Thresholds for Risk Levels
Level | Max Score | Comment
Low | 6 | Scores ≤ this are Low
Medium | 12 | Scores ≤ this are Medium
High | 19 | Scores ≤ this are High
Critical | 25 | Above High is Critical (max 25)

## Risk_Register
Risk Register — Identification, Assessment, Response & Monitoring (Automated)
ID | Category | Risk Title | Description | Cause | Consequence | Inh Likelihood (1-5) | Inh Impact (1-5) | Inh Score | Inh Level | Controls (Names) | Control Effectiveness | Res Likelihood (1-5) | Res Impact (1-5) | Res Score | Res Level | Owner | Response Strategy | Action IDs | Due Date | Status | Velocity | Review Date | Last Updated | Notes | Risk Code | Risk Age (days) | Next Review (auto) | Days to Review | Escalate?
1 | Operational | Stockout in critical SKUs | Demand spike and supplier delay | Single-source supplier | Lost sales, service level drop | 3 | 4 |  |  | Safety stock policy; reorder point | Moderate | 2 | 3 |  |  | Supply Manager | Reduce | A-001 | 2025-09-15 | Open | Fast | 2025-08-30 | 2025-08-15 | Increase alternate suppliers
2 | IT | Ransomware on ERP | Phishing leads to credential theft | Weak MFA adoption | Systems down, data loss | 3 | 5 |  |  | EDR + backups; awareness | Strong | 2 | 4 |  |  | CISO | Reduce | A-010 | 2025-08-31 | In progress | Fast | 2025-08-20 | 2025-08-15 | Rollout MFA company-wide
3 | Compliance | Late regulatory filings | Manual steps and lack of checklist | Process gaps | Fines and reputation | 3 | 4 |  |  | Checklist + deadline tracker | Moderate | 2 | 3 |  |  | Compliance Lead | Reduce | A-020 | 2025-10-10 | Open | Medium | 2025-08-10 | 2025-08-15 | Implement calendar alerts
4 | Financial | FX volatility on imports | Unhedged exposure | Rate swings | Margin erosion | 2 | 4 |  |  | Hedging policy | Moderate | 2 | 3 |  |  | Treasurer | Transfer | A-030 | 2025-09-30 | Open | Medium | 2025-08-18 | 2025-08-15 | Start forward contracts
5 | Security | Privilege escalation | Excessive admin rights | Poor RBAC | Data breaches | 3 | 4 |  |  | IAM reviews | Moderate | 2 | 3 |  |  | IT Sec Manager | Reduce | A-040 | 2025-09-05 | Open | Fast | 2025-08-22 | 2025-08-15 | Revoke unnecessary rights
6 | HSE | Forklift collisions | Narrow lanes | Layout constraints | Injury risk | 2 | 5 |  |  | Signage; training; speed control | Moderate | 1 | 4 |  |  | HSE Manager | Reduce | A-050 | 2025-09-25 | Open | Slow | 2025-08-15 | 2025-08-15 | Repaint lanes, add mirrors
7 | Project | Scope creep | Weak change control | Stakeholder requests | Budget/time overrun | 3 | 3 |  |  | Change board | Moderate | 2 | 3 |  |  | PMO | Avoid | A-060 | 2025-10-05 | Open | Medium | 2025-08-12 | 2025-08-15 | Enforce change requests
8 | Reputational | Social media backlash | Poor crisis response | Delayed communications | Brand damage | 2 | 4 |  |  | Crisis comms plan | Strong | 2 | 3 |  |  | Comms Director | Reduce | A-070 | 2025-09-18 | Open | Fast | 2025-08-25 | 2025-08-15 | Crisis playbook drills
9 | Strategic | Key customer churn | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-10-20 | Open | Medium | 2025-08-28 | 2025-08-15 | Renewal playbook
10 | Strategic | Key customer churn (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-09-10 | In progress | Fast | 2025-08-28 | 2025-08-15 | Renewal playbook (extended)
11 | Strategic | Key customer churn (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-10-15 | Open | Medium | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended)
12 | Strategic | Key customer churn (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-09-10 | In progress | Fast | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended)
13 | Strategic | Key customer churn (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-10-15 | Open | Medium | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended)
14 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-09-10 | In progress | Fast | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended)
15 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-10-15 | Open | Medium | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended)
16 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-09-10 | In progress | Fast | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended)
17 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-10-15 | Open | Medium | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended)
18 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-09-10 | In progress | Fast | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended)
19 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-10-15 | Open | Medium | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended)
20 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-09-10 | In progress | Fast | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended)
21 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-10-15 | Open | Medium | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended)
22 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-09-10 | In progress | Fast | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended)
23 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-10-15 | Open | Medium | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended)
24 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-09-10 | In progress | Fast | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended)
25 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-10-15 | Open | Medium | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended)
26 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-09-10 | In progress | Fast | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended)
27 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-10-15 | Open | Medium | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended)
28 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-09-10 | In progress | Fast | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended)
29 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-10-15 | Open | Medium | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended)
30 | Strategic | Key customer churn (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) (site B) | Weak value proposition | Competitor offers | Revenue loss | 3 | 4 |  |  | Customer success program | Moderate | 2 | 3 |  |  | Sales Director | Reduce | A-080 | 2025-09-10 | In progress | Fast | 2025-08-28 | 2025-08-15 | Renewal playbook (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended) (extended)
Formulas:
Risk Age (days) = IF([Last Updated]<>"",TODAY()-[Last Updated],"")
Next Review (auto) = IF([Velocity]="Fast",TODAY()+30,IF([Velocity]="Medium",TODAY()+60,TODAY()+90))
Days to Review = [Risk Age (days)]-TODAY()

## Controls_Library
Controls Library — Inventory & Effectiveness
Ctrl ID | Control Name | Type (Prev/Det/Cor) | Frequency | Owner | Effectiveness | Documentation | Notes
C-001 | Dual approval > threshold | Preventive | Per transaction | CFO | Strong | Policy AP-07; ERP rule
C-002 | Three-way match (PO/GRN/Invoice) | Preventive | Per transaction | AP Manager | Moderate | AP-09 procedure
C-003 | Supplier master review | Detective | Monthly | Procurement | Moderate | Vendor change log review
C-004 | User access review (ERP) | Detective | Quarterly | IT Sec | Strong | Access recertification report
C-005 | Backup restore test | Detective | Monthly | IT Ops | Moderate | Restore logs
C-006 | Patch management | Preventive | Monthly | IT Ops | Moderate | Patch calendar
C-007 | Anti-phishing awareness | Preventive | Quarterly | HR/IT | Moderate | Training records
C-008 | Incident response drill | Detective | Semi-annual | Security | Moderate | IR playbook
C-009 | SOX key controls testing | Detective | Quarterly | Internal Audit | Strong | Testing scripts
C-010 | Quality inspection sampling | Detective | Per batch | Quality | Moderate | QC checklist

## Action_Plan
Action Plan — Risk Treatment & Closure (Automated Health)
Action ID | Risk ID | Action | Owner | Priority | Due Date | % Complete | Status | Comment | Closed Date | Days Remaining | Overdue? | Health
A-001 | 1 | Qualify two alternate suppliers | Supply Manager | High | 2025-09-15 | 20% | Open | RFQ launched
A-002 | 1 | Revise safety stock parameters | Supply Manager | Medium | 2025-09-05 | 10% | Open | Param tuning
A-010 | 2 | Enforce MFA across ERP users | CISO | Critical | 2025-08-31 | 60% | In progress | Pilot completed
A-011 | 2 | Phishing simulation campaign | IT Sec | High | 2025-09-10 | 30% | Open | Campaign planned
A-020 | 3 | Regulatory calendar rollout | Compliance Lead | Medium | 2025-10-10 | 40% | Open | Template ready
A-030 | 4 | Execute forward contracts | Treasurer | High | 2025-09-30 | 20% | Open | Quotes requested
A-040 | 5 | Tighten admin rights | IT Sec Manager | High | 2025-09-05 | 50% | In progress | RBAC cleanup
A-050 | 6 | Repaint lanes, add mirrors | HSE Manager | Medium | 2025-09-25 | 30% | Open | Materials ordered
A-060 | 7 | Enforce change request form | PMO | High | 2025-10-05 | 20% | Open | Form drafted
A-070 | 8 | Crisis playbook drill | Comms Director | Medium | 2025-09-18 | 10% | Open | Drill scheduled
A-080 | 9 | Renewal playbook rollout | Sales Director | High | 2025-10-20 | 15% | Open | Kickoff set
A-112 | 4 | Generic mitigation step 12 | Owner 12 | Medium | 2025-10-15 | 10% | Open
A-113 | 5 | Generic mitigation step 13 | Owner 13 | Medium | 2025-10-15 | 10% | Open
A-114 | 6 | Generic mitigation step 14 | Owner 14 | Medium | 2025-10-15 | 10% | Open
A-115 | 7 | Generic mitigation step 15 | Owner 15 | Medium | 2025-10-15 | 10% | Open
A-116 | 8 | Generic mitigation step 16 | Owner 16 | Medium | 2025-10-15 | 10% | Open
A-117 | 9 | Generic mitigation step 17 | Owner 17 | Medium | 2025-10-15 | 10% | Open
A-118 | 1 | Generic mitigation step 18 | Owner 18 | Medium | 2025-10-15 | 10% | Open
A-119 | 2 | Generic mitigation step 19 | Owner 19 | Medium | 2025-10-15 | 10% | Open
A-120 | 3 | Generic mitigation step 20 | Owner 20 | Medium | 2025-10-15 | 10% | Open
Formulas:
Days Remaining = IF([Due Date]<>"",[Due Date]-TODAY(),"")
Overdue? = IF(AND([Status]<>"Closed",[Due Date]<TODAY()),"Yes","No")
Health = IF([Overdue?]="Yes","Late",IF(AND([Status]="In progress",G3<0.5,[Due Date]-TODAY()<=7),"At Risk","On Track"))

## Risk_Matrix
Risk Matrix — Inherent & Residual (5x5)
| INHERENT — Count of Risks |  |  |  |  | RESIDUAL — Count of Risks
| I1 | I2 | I3 | I4 | I5 | I1 | I2 | I3 | I4 | I5

## Dashboard
Dashboard — Risk KPIs & Distributions (Enhanced)
Total Risks |  | Residual Level | Count | Category | High+Critical
|  | Low |  | Strategic
High & Critical (Residual) |  | Medium |  | Financial
|  | High |  | Operational
Open Actions |  | Critical |  | Compliance
IT
Overdue Actions |  |  |  | Security
HSE
Due next 7 days (Actions) |  |  |  | Reputational
Project
Avg Residual Score
Velocity | Count
Fast
Medium
Slow

## Flux_Risque
Descendance des Flux — Processus de Gestion des Risques
1. Identification |  | 2. Évaluation |  | 3. Traitement |  | 4. Suivi & Reporting |  | 5. Réexamen
| → |  | → |  | → |  | →
Entrées & Sorties par étape
Étape | Entrées (Inputs) | Sorties (Outputs)
Identification | Incidents, audits, ateliers, SWOT, KRI, carto process | Registre initial des risques
Évaluation | L/I inhérents, contrôles, efficacité | Scores inhérents, niveaux, plan d'évaluation résiduelle
Traitement | Stratégie (A/R/T/A), plan d'action | Scores résiduels, propriétaires, échéances
Suivi & Reporting | Actions, statuts, KPI, incidents | Rappels, rapports, escalades
Réexamen | Changements, revues périodiques | Registre à jour, nouvelles priorités