## README_Mode_Emploi
MODE D'EMPLOI — Modèle Excel PESTEL (Automatisé) 1) Ajustez les seuils dans 'PESTEL_Params'. 2) Renseignez/éditez les facteurs dans 'PESTEL_Register'. 3) Ajoutez les actions dans 'Actions_PESTEL'. 4) Consultez 'PESTEL_Matrix' et 'Dashboard'. 5) Référez-vous à 'Flux_PESTEL' pour la descendance des flux. Automatisations : Score = Impact×Urgency, Priorité auto (Low/Med/High/Critical), Code par domaine (P/Ec/S/T/En/L), Prochaine revue auto (fréquence), jours restants, escalade si High/Critical non clos, surlignage retards.

## PESTEL_Params
PESTEL Parameters — Thresholds for Priority
Priority Level | Max Score | Comment
Low | 6 | Scores ≤ this are Low
Medium | 12 | Scores ≤ this are Medium
High | 19 | Scores ≤ this are High
Critical | 25 | Above High is Critical (max 25)
Domains legend
Political
Economic
Social
Technological
Environmental
Legal

## PESTEL_Register
PESTEL Register — Scanning, Assessment, Prioritization & Monitoring
ID | Domain | Factor Title | Description | Evidence/Source | Geography | Affected Units | Time Horizon | Trend | Direction | Impact (1-5) | Urgency (1-5) | Score | Priority Level | Owner | Strategy | Action IDs | Due Date | Status | Review Frequency | Next Review (auto) | Days to Review | Escalate? | Last Updated | Notes | Code | Age (days)
1 | Political | New data sovereignty rules | Draft bill requiring local data storage | Gov portal | EU | IT, Legal | 1-3y | Up | Threat | 4 | 3 |  |  | CIO | Mitigate | AP-101 | 2025-10-15 | Open | Quarterly |  |  |  | 2025-08-10 | Assess data residency options
2 | Political | Public subsidies for green tech | Funding program for industrial decarbonization | Official gazette | National | Ops, Finance | 6-12m | Stable | Opportunity | 3 | 4 |  |  | Sustainability Lead | Leverage | AP-201 | 2025-11-30 | Open | Semiannual |  |  |  | 2025-08-05 | Prepare application dossier
3 | Economic | FX volatility on imports | Currency swings affecting BOM costs | Market reports | Global | Procurement | Now | Up | Threat | 4 | 5 |  |  | Treasurer | Transfer | AP-301 | 2025-09-30 | In progress | Monthly |  |  |  | 2025-08-18 | Forward contracts pipeline
4 | Economic | Lower interest rates | Cheaper financing conditions expected | Central bank outlook | EU | Finance | 1-3y | Down | Opportunity | 3 | 3 |  |  | CFO | Leverage | AP-302 | 2025-12-15 | Open | Quarterly |  |  |  | 2025-08-01 | Refinance capex
5 | Social | Talent shortage in data | Competition for data engineers | Recruiting stats | Local | HR, IT | 6-12m | Up | Threat | 4 | 4 |  |  | HR Director | Mitigate | AP-401 | 2025-10-05 | Open | Quarterly |  |  |  | 2025-08-12 | Partnerships with schools
6 | Social | Consumer eco-awareness | Demand for low-carbon products | Survey data | EU | Marketing | 1-3y | Up | Opportunity | 3 | 4 |  |  | CMO | Leverage | AP-402 | 2025-09-25 | Open | Semiannual |  |  |  | 2025-08-14 | Green product labeling
7 | Technological | AI-enabled automation | Mature tools for process automation | Vendor demos | Ops | Ops, IT | 6-12m | Up | Opportunity | 4 | 4 |  |  | COO | Leverage | AP-501 | 2025-10-20 | Open | Quarterly |  |  |  | 2025-08-20 | Pilot RPA/AI in back-office
8 | Technological | Legacy ERP constraints | Customization limits and maintenance costs | IT audit | HQ | IT | 1-3y | Stable | Threat | 3 | 3 |  |  | CIO | Mitigate | AP-502 | 2025-11-10 | Open | Quarterly |  |  |  | 2025-08-16 | Roadmap to modernize
9 | Environmental | Tighter emissions caps | Stricter ETS phase | Regulator note | EU | Plants | 1-3y | Up | Threat | 5 | 4 |  |  | Plant Manager | Mitigate | AP-601 | 2025-09-18 | Open | Quarterly |  |  |  | 2025-08-22 | Capex for abatement
10 | Environmental | Renewable energy incentives | Accelerated depreciation for solar | Gov circular | National | All sites | 6-12m | Stable | Opportunity | 3 | 4 |  |  | Energy Manager | Leverage | AP-602 | 2025-10-30 | Open | Semiannual |  |  |  | 2025-08-07 | Solar PPA assessment
11 | Legal | Privacy regulation update | Stronger consent requirements | DP authority note | EU | Legal, Marketing | 6-12m | Up | Threat | 4 | 4 |  |  | DPO | Mitigate | AP-701 | 2025-09-12 | Open | Quarterly |  |  |  | 2025-08-25 | Consent framework redesign
12 | Legal | Whistleblowing protections | Expanded scope & deadlines | Official bulletin | National | HR, Legal | Now | Stable | Threat | 3 | 3 |  |  | Legal Counsel | Mitigate | AP-702 | 2025-08-31 | In progress | Monthly |  |  |  | 2025-08-19 | Update policy & channel
13 | Political | New data sovereignty rules (alt) | Draft bill requiring local data storage | Gov portal | EU | IT, Legal / Div2 | 1-3y | Up | Threat | 4 | 3 |  |  | CIO | Mitigate | AP-101 | 2025-10-15 | In progress | Quarterly |  |  |  | 2025-08-10 | Assess data residency options
14 | Political | Public subsidies for green tech (alt) | Funding program for industrial decarbonization | Official gazette | National | Ops, Finance / Div2 | 6-12m | Stable | Opportunity | 3 | 4 |  |  | Sustainability Lead | Leverage | AP-201 | 2025-11-30 | In progress | Semiannual |  |  |  | 2025-08-05 | Prepare application dossier
15 | Economic | FX volatility on imports (alt) | Currency swings affecting BOM costs | Market reports | Global | Procurement / Div2 | Now | Up | Threat | 4 | 5 |  |  | Treasurer | Transfer | AP-301 | 2025-09-30 | Open | Monthly |  |  |  | 2025-08-18 | Forward contracts pipeline
16 | Economic | Lower interest rates (alt) | Cheaper financing conditions expected | Central bank outlook | EU | Finance / Div2 | 1-3y | Down | Opportunity | 3 | 3 |  |  | CFO | Leverage | AP-302 | 2025-12-15 | In progress | Quarterly |  |  |  | 2025-08-01 | Refinance capex
17 | Social | Talent shortage in data (alt) | Competition for data engineers | Recruiting stats | Local | HR, IT / Div2 | 6-12m | Up | Threat | 4 | 4 |  |  | HR Director | Mitigate | AP-401 | 2025-10-05 | In progress | Quarterly |  |  |  | 2025-08-12 | Partnerships with schools
18 | Social | Consumer eco-awareness (alt) | Demand for low-carbon products | Survey data | EU | Marketing / Div2 | 1-3y | Up | Opportunity | 3 | 4 |  |  | CMO | Leverage | AP-402 | 2025-09-25 | In progress | Semiannual |  |  |  | 2025-08-14 | Green product labeling
19 | Technological | AI-enabled automation (alt) | Mature tools for process automation | Vendor demos | Ops | Ops, IT / Div2 | 6-12m | Up | Opportunity | 4 | 4 |  |  | COO | Leverage | AP-501 | 2025-10-20 | In progress | Quarterly |  |  |  | 2025-08-20 | Pilot RPA/AI in back-office
20 | Technological | Legacy ERP constraints (alt) | Customization limits and maintenance costs | IT audit | HQ | IT / Div2 | 1-3y | Stable | Threat | 3 | 3 |  |  | CIO | Mitigate | AP-502 | 2025-11-10 | In progress | Quarterly |  |  |  | 2025-08-16 | Roadmap to modernize
21 | Environmental | Tighter emissions caps (alt) | Stricter ETS phase | Regulator note | EU | Plants / Div2 | 1-3y | Up | Threat | 5 | 4 |  |  | Plant Manager | Mitigate | AP-601 | 2025-09-18 | In progress | Quarterly |  |  |  | 2025-08-22 | Capex for abatement
22 | Environmental | Renewable energy incentives (alt) | Accelerated depreciation for solar | Gov circular | National | All sites / Div2 | 6-12m | Stable | Opportunity | 3 | 4 |  |  | Energy Manager | Leverage | AP-602 | 2025-10-30 | In progress | Semiannual |  |  |  | 2025-08-07 | Solar PPA assessment
23 | Legal | Privacy regulation update (alt) | Stronger consent requirements | DP authority note | EU | Legal, Marketing / Div2 | 6-12m | Up | Threat | 4 | 4 |  |  | DPO | Mitigate | AP-701 | 2025-09-12 | In progress | Quarterly |  |  |  | 2025-08-25 | Consent framework redesign
24 | Legal | Whistleblowing protections (alt) | Expanded scope & deadlines | Official bulletin | National | HR, Legal / Div2 | Now | Stable | Threat | 3 | 3 |  |  | Legal Counsel | Mitigate | AP-702 | 2025-08-31 | Open | Monthly |  |  |  | 2025-08-19 | Update policy & channel
Formulas:
Next Review (auto) = IF([Review Frequency]="Monthly",TODAY()+30,IF([Review Frequency]="Quarterly",TODAY()+90,IF([Review Frequency]="Semiannual",TODAY()+180,IF([Review Frequency]="Annual",TODAY()+365,""))))
Days to Review = IF([Next Review (auto)]<>"",[Next Review (auto)]-TODAY(),"")
Age (days) = IF([Last Updated]<>"",TODAY()-[Last Updated],"")

## Actions_PESTEL
Actions — PESTEL Response & Execution
Action ID | Factor ID | Action | Owner | Priority | Due Date | % Complete | Status | Comment | Closed Date | Days Remaining | Overdue? | Health
AP-101 | 1 | Assess data residency & options | CIO | High | 2025-10-15 | 20% | Open | Map data flows
AP-201 | 2 | Prepare funding dossier | Sustainability Lead | Medium | 2025-11-30 | 10% | Open | Gather docs
AP-301 | 3 | Execute hedging program | Treasurer | High | 2025-09-30 | 50% | In progress | Forward contracts
AP-402 | 6 | Launch green labeling | CMO | High | 2025-09-25 | 20% | Open | Design labels
AP-601 | 9 | Plan abatement capex | Plant Manager | Critical | 2025-09-18 | 30% | Open | Vendor shortlist
AP-701 | 11 | Redesign consent framework | DPO | High | 2025-09-12 | 40% | In progress | Templates drafted
AP-807 | 8 | Generic PESTEL action 7 | Owner 7 | Medium | 2025-10-20 | 10% | Open
AP-808 | 9 | Generic PESTEL action 8 | Owner 8 | Medium | 2025-10-20 | 10% | Open
AP-809 | 10 | Generic PESTEL action 9 | Owner 9 | Medium | 2025-10-20 | 10% | Open
AP-810 | 11 | Generic PESTEL action 10 | Owner 10 | Medium | 2025-10-20 | 10% | Open
AP-811 | 12 | Generic PESTEL action 11 | Owner 11 | Medium | 2025-10-20 | 10% | Open
AP-812 | 1 | Generic PESTEL action 12 | Owner 12 | Medium | 2025-10-20 | 10% | Open
AP-813 | 2 | Generic PESTEL action 13 | Owner 13 | Medium | 2025-10-20 | 10% | Open
AP-814 | 3 | Generic PESTEL action 14 | Owner 14 | Medium | 2025-10-20 | 10% | Open
AP-815 | 4 | Generic PESTEL action 15 | Owner 15 | Medium | 2025-10-20 | 10% | Open
Formulas:
Days Remaining = IF([Due Date]<>"",[Due Date]-TODAY(),"")
Overdue? = IF(AND([Status]<>"Closed",[Due Date]<TODAY()),"Yes","No")
Health = IF([Overdue?]="Yes","Late",IF(AND([Status]="In progress",G3<0.5,[Due Date]-TODAY()<=7),"At Risk","On Track"))

## PESTEL_Matrix
PESTEL Matrices — Domain×Horizon & Impact×Horizon
Domain × Horizon |  |  |  |  | Impact × Horizon
| Now | 6-12m | 1-3y | 3+y |  | Now | 6-12m | 1-3y | 3+y
Political |  |  |  |  | I1
Economic |  |  |  |  | I2
Social |  |  |  |  | I3
Technological |  |  |  |  | I4
Environmental |  |  |  |  | I5
Legal

## Dashboard
Dashboard — PESTEL KPIs & Distributions
Total Factors | Domain | Count | Priority | Count
| Political |  | Low
High+Critical (Priority) | Economic |  | Medium
| Social |  | High
Opportunities | Technological |  | Critical
Environmental
Threats | Legal
Open Actions
Overdue Actions
Reviews due ≤7d

## Flux_PESTEL
Descendance des Flux — Processus PESTEL
1. Veille/Scanning |  | 2. Identification |  | 3. Qualification |  | 4. Priorisation |  | 5. Décision & Plan d’actions |  | 6. Exécution |  | 7. Suivi & Réexamen
| → |  | → |  | → |  | → |  | → |  | →
Entrées & Sorties par étape
Étape | Entrées (Inputs) | Sorties (Outputs)
Veille/Scanning | Newsletters, régulateurs, think tanks, réseaux, benchmarks | Flux d’information qualifié
Identification | Signaux de l’environnement, alertes internes | Liste de facteurs PESTEL bruts
Qualification | Description, preuves, périmètre, horizon, tendance | Facteurs qualifiés (fiche)
Priorisation | Impact×Urgence, appétence, direction Opp/Threat | Niveaux Low/Med/High/Critical
Décision & Plan d’actions | Facteurs priorisés, propriétaires, options | Décisions, actions et échéances
Exécution | Plan d’actions, moyens | Actions réalisées, livrables
Suivi & Réexamen | KPI/KRI, incidents, changements | Registre à jour, escalades, nouveaux signaux