{"text_format":"3","workbook":"xlsx","n_sheets":11,"sheets":["PQP_Grandes_Lignes","Exigences_Client","Descendance_Flux","WBS_Livrables","Essais_Validation","Actions_CAPA","Risque_Qualite","Timeline","RACI","Communication","KPI_Dashboard"],"read":"whole","date_system":"1900"}

{"sheet":"PQP_Grandes_Lignes","index":0,"n_rows":20,"n_cols":2,"rows_kept":20}
["Plan Qualité Projet — Grandes Lignes"]
[]
["Champ","Valeur"]
["Titre Projet","PROJET X – Plan Qualité Projet (PQP)"]
["Client","Client ABC"]
["Référence","PQP-2025-001"]
["Version","v1.0"]
["Date"]
["Chef de Projet"]
["Périmètre","Produit Ligne A – site A"]
["Objectifs Qualité","PPM<500, FPY≥98%, 100% traçabilité, CE obtenu"]
[]
[]
["Palette & codes"]
["Couleur","Usage"]
["#1F4E79","En-têtes / Qualité"]
["#2E7D32","KPIs / Validation"]
["#FF8F00","Alertes / Échéances proches"]
["#C62828","Non-conformités / Critiques"]
["#455A64","Neutre / Info"]

{"sheet":"Exigences_Client","index":1,"n_rows":13,"n_cols":11,"rows_kept":13}
["Exigences Client & Traçabilité"]
[]
["ID Exigence","Description","Source","Catégorie","Priorité","Processus","Méthode de vérif.","Pilote","Statut","Date d'ouverture","Lien/Doc"]
["REQ-001","Contrôle dimensionnel ±0,1 mm","Client ABC","Produit","Haut","Qualité","Mesure","Resp Qualité","Ouverte","2025-08-22"]
["REQ-002","Traçabilité lot 100%","Client ABC","Process","Haut","Qualité","Audit","Resp Méthodes","En cours","2025-08-22"]
["REQ-003","Rendement FPY ≥ 98%","Contrat","Performance","Moyen","Prod","Essai","Resp Prod","Ouverte","2025-08-22"]
["REQ-004","Délai réponse réclamation ≤ 48h","Client ABC","Service","Moyen","Qualité","Process audit","Resp Qualité","Ouverte","2025-08-22"]
["REQ-005","Marquage CE conforme","Réglementaire","Conformité","Haut","QHSE","Inspection","HSE","Ouverte","2025-08-22"]
["REQ-006","Bruit < 70 dB(A) @1m","Spéc Tech","Performance","Moyen","R&D","Essai","R&D","Ouverte","2025-08-22"]
["REQ-007","Matériau RoHS/REACH","Réglementaire","Conformité","Haut","Achat","Certificat","Achat","Ouverte","2025-08-22"]
["REQ-008","MTBF ≥ 20 000 h","Spéc Tech","Fiabilité","Moyen","R&D","Essai longue durée","R&D","Ouverte","2025-08-22"]
["REQ-009","PPM Client < 500","Contrat","Qualité","Moyen","Qualité","Reporting","Resp Qualité","Ouverte","2025-08-22"]
["REQ-010","Emballage recyclable 100%","Client ABC","Environnement","Bas","QHSE","Spéc emballage","HSE","Ouverte","2025-08-22"]

{"sheet":"Descendance_Flux","index":2,"n_rows":406,"n_cols":8,"rows_kept":406}
["Descendance des Flux d'information (Flow-Down)"]
[]
["Exigence ID","Spec interne / Doc","Process/Contrôle","Essai/Validation","Rapport/Preuve","Propriétaire","Statut","FirstOccur"]
["REQ-001","SPEC-PRD-01 v1","CP-LigneA v2","TEST-001","RPT-001","Resp Qualité","En cours",{"$f":"IF($A4=\"\",\"\",IF(COUNTIF($A$4:$A4,$A4)=1,1,0))","v":0}]
["REQ-001","SPEC-PRD-01 v1","CP-LigneA v2","TEST-002","RPT-002","Resp Qualité","Ouverte",{"$f":"IF($A5=\"\",\"\",IF(COUNTIF($A$4:$A5,$A5)=1,1,0))","v":0}]
["REQ-002","SPEC-TRAC-02 v3","PROC-TRAC v1","AUD-TRAC-01","RPT-003","Resp Méthodes","En cours",{"$f":"IF($A6=\"\",\"\",IF(COUNTIF($A$4:$A6,$A6)=1,1,0))","v":0}]
["REQ-003","SPEC-PERF-01","PROC-FPY v2","TEST-FPY-01","RPT-004","Resp Prod","Ouverte",{"$f":"IF($A7=\"\",\"\",IF(COUNTIF($A$4:$A7,$A7)=1,1,0))","v":0}]
["REQ-005","SPEC-CE-REG","PROC-CE v1","CHECK-CE-01","CERT-CE-01","HSE","Ouverte",{"$f":"IF($A8=\"\",\"\",IF(COUNTIF($A$4:$A8,$A8)=1,1,0))","v":0}]
["REQ-007","SPEC-REACH","PROC-REACH","CERT-ROHS","DOSSIER-REACH","Achat","Ouverte",{"$f":"IF($A9=\"\",\"\",IF(COUNTIF($A$4:$A9,$A9)=1,1,0))","v":0}]
["REQ-008","SPEC-FIAB","PLAN-LD-01","TEST-LD-01","RPT-LD-01","R&D","Ouverte",{"$f":"IF($A10=\"\",\"\",IF(COUNTIF($A$4:$A10,$A10)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A11=\"\",\"\",IF(COUNTIF($A$4:$A11,$A11)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A12=\"\",\"\",IF(COUNTIF($A$4:$A12,$A12)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A13=\"\",\"\",IF(COUNTIF($A$4:$A13,$A13)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A14=\"\",\"\",IF(COUNTIF($A$4:$A14,$A14)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A15=\"\",\"\",IF(COUNTIF($A$4:$A15,$A15)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A16=\"\",\"\",IF(COUNTIF($A$4:$A16,$A16)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A17=\"\",\"\",IF(COUNTIF($A$4:$A17,$A17)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A18=\"\",\"\",IF(COUNTIF($A$4:$A18,$A18)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A19=\"\",\"\",IF(COUNTIF($A$4:$A19,$A19)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A20=\"\",\"\",IF(COUNTIF($A$4:$A20,$A20)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A21=\"\",\"\",IF(COUNTIF($A$4:$A21,$A21)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A22=\"\",\"\",IF(COUNTIF($A$4:$A22,$A22)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A23=\"\",\"\",IF(COUNTIF($A$4:$A23,$A23)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A24=\"\",\"\",IF(COUNTIF($A$4:$A24,$A24)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A25=\"\",\"\",IF(COUNTIF($A$4:$A25,$A25)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A26=\"\",\"\",IF(COUNTIF($A$4:$A26,$A26)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A27=\"\",\"\",IF(COUNTIF($A$4:$A27,$A27)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A28=\"\",\"\",IF(COUNTIF($A$4:$A28,$A28)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A29=\"\",\"\",IF(COUNTIF($A$4:$A29,$A29)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A30=\"\",\"\",IF(COUNTIF($A$4:$A30,$A30)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A31=\"\",\"\",IF(COUNTIF($A$4:$A31,$A31)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A32=\"\",\"\",IF(COUNTIF($A$4:$A32,$A32)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A33=\"\",\"\",IF(COUNTIF($A$4:$A33,$A33)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A34=\"\",\"\",IF(COUNTIF($A$4:$A34,$A34)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A35=\"\",\"\",IF(COUNTIF($A$4:$A35,$A35)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A36=\"\",\"\",IF(COUNTIF($A$4:$A36,$A36)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A37=\"\",\"\",IF(COUNTIF($A$4:$A37,$A37)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A38=\"\",\"\",IF(COUNTIF($A$4:$A38,$A38)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A39=\"\",\"\",IF(COUNTIF($A$4:$A39,$A39)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A40=\"\",\"\",IF(COUNTIF($A$4:$A40,$A40)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A41=\"\",\"\",IF(COUNTIF($A$4:$A41,$A41)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A42=\"\",\"\",IF(COUNTIF($A$4:$A42,$A42)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A43=\"\",\"\",IF(COUNTIF($A$4:$A43,$A43)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A44=\"\",\"\",IF(COUNTIF($A$4:$A44,$A44)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A45=\"\",\"\",IF(COUNTIF($A$4:$A45,$A45)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A46=\"\",\"\",IF(COUNTIF($A$4:$A46,$A46)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A47=\"\",\"\",IF(COUNTIF($A$4:$A47,$A47)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A48=\"\",\"\",IF(COUNTIF($A$4:$A48,$A48)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A49=\"\",\"\",IF(COUNTIF($A$4:$A49,$A49)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A50=\"\",\"\",IF(COUNTIF($A$4:$A50,$A50)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A51=\"\",\"\",IF(COUNTIF($A$4:$A51,$A51)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A52=\"\",\"\",IF(COUNTIF($A$4:$A52,$A52)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A53=\"\",\"\",IF(COUNTIF($A$4:$A53,$A53)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A54=\"\",\"\",IF(COUNTIF($A$4:$A54,$A54)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A55=\"\",\"\",IF(COUNTIF($A$4:$A55,$A55)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A56=\"\",\"\",IF(COUNTIF($A$4:$A56,$A56)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A57=\"\",\"\",IF(COUNTIF($A$4:$A57,$A57)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A58=\"\",\"\",IF(COUNTIF($A$4:$A58,$A58)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A59=\"\",\"\",IF(COUNTIF($A$4:$A59,$A59)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A60=\"\",\"\",IF(COUNTIF($A$4:$A60,$A60)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A61=\"\",\"\",IF(COUNTIF($A$4:$A61,$A61)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A62=\"\",\"\",IF(COUNTIF($A$4:$A62,$A62)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A63=\"\",\"\",IF(COUNTIF($A$4:$A63,$A63)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A64=\"\",\"\",IF(COUNTIF($A$4:$A64,$A64)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A65=\"\",\"\",IF(COUNTIF($A$4:$A65,$A65)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A66=\"\",\"\",IF(COUNTIF($A$4:$A66,$A66)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A67=\"\",\"\",IF(COUNTIF($A$4:$A67,$A67)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A68=\"\",\"\",IF(COUNTIF($A$4:$A68,$A68)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A69=\"\",\"\",IF(COUNTIF($A$4:$A69,$A69)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A70=\"\",\"\",IF(COUNTIF($A$4:$A70,$A70)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A71=\"\",\"\",IF(COUNTIF($A$4:$A71,$A71)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A72=\"\",\"\",IF(COUNTIF($A$4:$A72,$A72)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A73=\"\",\"\",IF(COUNTIF($A$4:$A73,$A73)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A74=\"\",\"\",IF(COUNTIF($A$4:$A74,$A74)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A75=\"\",\"\",IF(COUNTIF($A$4:$A75,$A75)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A76=\"\",\"\",IF(COUNTIF($A$4:$A76,$A76)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A77=\"\",\"\",IF(COUNTIF($A$4:$A77,$A77)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A78=\"\",\"\",IF(COUNTIF($A$4:$A78,$A78)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A79=\"\",\"\",IF(COUNTIF($A$4:$A79,$A79)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A80=\"\",\"\",IF(COUNTIF($A$4:$A80,$A80)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A81=\"\",\"\",IF(COUNTIF($A$4:$A81,$A81)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A82=\"\",\"\",IF(COUNTIF($A$4:$A82,$A82)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A83=\"\",\"\",IF(COUNTIF($A$4:$A83,$A83)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A84=\"\",\"\",IF(COUNTIF($A$4:$A84,$A84)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A85=\"\",\"\",IF(COUNTIF($A$4:$A85,$A85)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A86=\"\",\"\",IF(COUNTIF($A$4:$A86,$A86)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A87=\"\",\"\",IF(COUNTIF($A$4:$A87,$A87)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A88=\"\",\"\",IF(COUNTIF($A$4:$A88,$A88)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A89=\"\",\"\",IF(COUNTIF($A$4:$A89,$A89)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A90=\"\",\"\",IF(COUNTIF($A$4:$A90,$A90)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A91=\"\",\"\",IF(COUNTIF($A$4:$A91,$A91)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A92=\"\",\"\",IF(COUNTIF($A$4:$A92,$A92)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A93=\"\",\"\",IF(COUNTIF($A$4:$A93,$A93)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A94=\"\",\"\",IF(COUNTIF($A$4:$A94,$A94)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A95=\"\",\"\",IF(COUNTIF($A$4:$A95,$A95)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A96=\"\",\"\",IF(COUNTIF($A$4:$A96,$A96)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A97=\"\",\"\",IF(COUNTIF($A$4:$A97,$A97)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A98=\"\",\"\",IF(COUNTIF($A$4:$A98,$A98)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A99=\"\",\"\",IF(COUNTIF($A$4:$A99,$A99)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A100=\"\",\"\",IF(COUNTIF($A$4:$A100,$A100)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A101=\"\",\"\",IF(COUNTIF($A$4:$A101,$A101)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A102=\"\",\"\",IF(COUNTIF($A$4:$A102,$A102)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A103=\"\",\"\",IF(COUNTIF($A$4:$A103,$A103)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A104=\"\",\"\",IF(COUNTIF($A$4:$A104,$A104)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A105=\"\",\"\",IF(COUNTIF($A$4:$A105,$A105)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A106=\"\",\"\",IF(COUNTIF($A$4:$A106,$A106)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A107=\"\",\"\",IF(COUNTIF($A$4:$A107,$A107)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A108=\"\",\"\",IF(COUNTIF($A$4:$A108,$A108)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A109=\"\",\"\",IF(COUNTIF($A$4:$A109,$A109)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A110=\"\",\"\",IF(COUNTIF($A$4:$A110,$A110)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A111=\"\",\"\",IF(COUNTIF($A$4:$A111,$A111)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A112=\"\",\"\",IF(COUNTIF($A$4:$A112,$A112)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A113=\"\",\"\",IF(COUNTIF($A$4:$A113,$A113)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A114=\"\",\"\",IF(COUNTIF($A$4:$A114,$A114)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A115=\"\",\"\",IF(COUNTIF($A$4:$A115,$A115)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A116=\"\",\"\",IF(COUNTIF($A$4:$A116,$A116)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A117=\"\",\"\",IF(COUNTIF($A$4:$A117,$A117)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A118=\"\",\"\",IF(COUNTIF($A$4:$A118,$A118)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A119=\"\",\"\",IF(COUNTIF($A$4:$A119,$A119)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A120=\"\",\"\",IF(COUNTIF($A$4:$A120,$A120)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A121=\"\",\"\",IF(COUNTIF($A$4:$A121,$A121)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A122=\"\",\"\",IF(COUNTIF($A$4:$A122,$A122)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A123=\"\",\"\",IF(COUNTIF($A$4:$A123,$A123)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A124=\"\",\"\",IF(COUNTIF($A$4:$A124,$A124)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A125=\"\",\"\",IF(COUNTIF($A$4:$A125,$A125)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A126=\"\",\"\",IF(COUNTIF($A$4:$A126,$A126)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A127=\"\",\"\",IF(COUNTIF($A$4:$A127,$A127)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A128=\"\",\"\",IF(COUNTIF($A$4:$A128,$A128)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A129=\"\",\"\",IF(COUNTIF($A$4:$A129,$A129)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A130=\"\",\"\",IF(COUNTIF($A$4:$A130,$A130)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A131=\"\",\"\",IF(COUNTIF($A$4:$A131,$A131)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A132=\"\",\"\",IF(COUNTIF($A$4:$A132,$A132)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A133=\"\",\"\",IF(COUNTIF($A$4:$A133,$A133)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A134=\"\",\"\",IF(COUNTIF($A$4:$A134,$A134)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A135=\"\",\"\",IF(COUNTIF($A$4:$A135,$A135)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A136=\"\",\"\",IF(COUNTIF($A$4:$A136,$A136)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A137=\"\",\"\",IF(COUNTIF($A$4:$A137,$A137)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A138=\"\",\"\",IF(COUNTIF($A$4:$A138,$A138)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A139=\"\",\"\",IF(COUNTIF($A$4:$A139,$A139)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A140=\"\",\"\",IF(COUNTIF($A$4:$A140,$A140)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A141=\"\",\"\",IF(COUNTIF($A$4:$A141,$A141)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A142=\"\",\"\",IF(COUNTIF($A$4:$A142,$A142)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A143=\"\",\"\",IF(COUNTIF($A$4:$A143,$A143)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A144=\"\",\"\",IF(COUNTIF($A$4:$A144,$A144)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A145=\"\",\"\",IF(COUNTIF($A$4:$A145,$A145)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A146=\"\",\"\",IF(COUNTIF($A$4:$A146,$A146)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A147=\"\",\"\",IF(COUNTIF($A$4:$A147,$A147)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A148=\"\",\"\",IF(COUNTIF($A$4:$A148,$A148)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A149=\"\",\"\",IF(COUNTIF($A$4:$A149,$A149)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A150=\"\",\"\",IF(COUNTIF($A$4:$A150,$A150)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A151=\"\",\"\",IF(COUNTIF($A$4:$A151,$A151)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A152=\"\",\"\",IF(COUNTIF($A$4:$A152,$A152)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A153=\"\",\"\",IF(COUNTIF($A$4:$A153,$A153)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A154=\"\",\"\",IF(COUNTIF($A$4:$A154,$A154)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A155=\"\",\"\",IF(COUNTIF($A$4:$A155,$A155)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A156=\"\",\"\",IF(COUNTIF($A$4:$A156,$A156)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A157=\"\",\"\",IF(COUNTIF($A$4:$A157,$A157)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A158=\"\",\"\",IF(COUNTIF($A$4:$A158,$A158)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A159=\"\",\"\",IF(COUNTIF($A$4:$A159,$A159)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A160=\"\",\"\",IF(COUNTIF($A$4:$A160,$A160)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A161=\"\",\"\",IF(COUNTIF($A$4:$A161,$A161)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A162=\"\",\"\",IF(COUNTIF($A$4:$A162,$A162)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A163=\"\",\"\",IF(COUNTIF($A$4:$A163,$A163)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A164=\"\",\"\",IF(COUNTIF($A$4:$A164,$A164)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A165=\"\",\"\",IF(COUNTIF($A$4:$A165,$A165)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A166=\"\",\"\",IF(COUNTIF($A$4:$A166,$A166)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A167=\"\",\"\",IF(COUNTIF($A$4:$A167,$A167)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A168=\"\",\"\",IF(COUNTIF($A$4:$A168,$A168)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A169=\"\",\"\",IF(COUNTIF($A$4:$A169,$A169)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A170=\"\",\"\",IF(COUNTIF($A$4:$A170,$A170)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A171=\"\",\"\",IF(COUNTIF($A$4:$A171,$A171)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A172=\"\",\"\",IF(COUNTIF($A$4:$A172,$A172)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A173=\"\",\"\",IF(COUNTIF($A$4:$A173,$A173)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A174=\"\",\"\",IF(COUNTIF($A$4:$A174,$A174)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A175=\"\",\"\",IF(COUNTIF($A$4:$A175,$A175)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A176=\"\",\"\",IF(COUNTIF($A$4:$A176,$A176)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A177=\"\",\"\",IF(COUNTIF($A$4:$A177,$A177)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A178=\"\",\"\",IF(COUNTIF($A$4:$A178,$A178)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A179=\"\",\"\",IF(COUNTIF($A$4:$A179,$A179)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A180=\"\",\"\",IF(COUNTIF($A$4:$A180,$A180)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A181=\"\",\"\",IF(COUNTIF($A$4:$A181,$A181)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A182=\"\",\"\",IF(COUNTIF($A$4:$A182,$A182)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A183=\"\",\"\",IF(COUNTIF($A$4:$A183,$A183)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A184=\"\",\"\",IF(COUNTIF($A$4:$A184,$A184)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A185=\"\",\"\",IF(COUNTIF($A$4:$A185,$A185)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A186=\"\",\"\",IF(COUNTIF($A$4:$A186,$A186)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A187=\"\",\"\",IF(COUNTIF($A$4:$A187,$A187)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A188=\"\",\"\",IF(COUNTIF($A$4:$A188,$A188)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A189=\"\",\"\",IF(COUNTIF($A$4:$A189,$A189)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A190=\"\",\"\",IF(COUNTIF($A$4:$A190,$A190)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A191=\"\",\"\",IF(COUNTIF($A$4:$A191,$A191)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A192=\"\",\"\",IF(COUNTIF($A$4:$A192,$A192)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A193=\"\",\"\",IF(COUNTIF($A$4:$A193,$A193)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A194=\"\",\"\",IF(COUNTIF($A$4:$A194,$A194)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A195=\"\",\"\",IF(COUNTIF($A$4:$A195,$A195)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A196=\"\",\"\",IF(COUNTIF($A$4:$A196,$A196)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A197=\"\",\"\",IF(COUNTIF($A$4:$A197,$A197)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A198=\"\",\"\",IF(COUNTIF($A$4:$A198,$A198)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A199=\"\",\"\",IF(COUNTIF($A$4:$A199,$A199)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A200=\"\",\"\",IF(COUNTIF($A$4:$A200,$A200)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A201=\"\",\"\",IF(COUNTIF($A$4:$A201,$A201)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A202=\"\",\"\",IF(COUNTIF($A$4:$A202,$A202)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A203=\"\",\"\",IF(COUNTIF($A$4:$A203,$A203)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A204=\"\",\"\",IF(COUNTIF($A$4:$A204,$A204)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A205=\"\",\"\",IF(COUNTIF($A$4:$A205,$A205)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A206=\"\",\"\",IF(COUNTIF($A$4:$A206,$A206)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A207=\"\",\"\",IF(COUNTIF($A$4:$A207,$A207)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A208=\"\",\"\",IF(COUNTIF($A$4:$A208,$A208)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A209=\"\",\"\",IF(COUNTIF($A$4:$A209,$A209)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A210=\"\",\"\",IF(COUNTIF($A$4:$A210,$A210)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A211=\"\",\"\",IF(COUNTIF($A$4:$A211,$A211)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A212=\"\",\"\",IF(COUNTIF($A$4:$A212,$A212)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A213=\"\",\"\",IF(COUNTIF($A$4:$A213,$A213)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A214=\"\",\"\",IF(COUNTIF($A$4:$A214,$A214)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A215=\"\",\"\",IF(COUNTIF($A$4:$A215,$A215)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A216=\"\",\"\",IF(COUNTIF($A$4:$A216,$A216)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A217=\"\",\"\",IF(COUNTIF($A$4:$A217,$A217)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A218=\"\",\"\",IF(COUNTIF($A$4:$A218,$A218)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A219=\"\",\"\",IF(COUNTIF($A$4:$A219,$A219)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A220=\"\",\"\",IF(COUNTIF($A$4:$A220,$A220)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A221=\"\",\"\",IF(COUNTIF($A$4:$A221,$A221)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A222=\"\",\"\",IF(COUNTIF($A$4:$A222,$A222)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A223=\"\",\"\",IF(COUNTIF($A$4:$A223,$A223)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A224=\"\",\"\",IF(COUNTIF($A$4:$A224,$A224)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A225=\"\",\"\",IF(COUNTIF($A$4:$A225,$A225)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A226=\"\",\"\",IF(COUNTIF($A$4:$A226,$A226)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A227=\"\",\"\",IF(COUNTIF($A$4:$A227,$A227)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A228=\"\",\"\",IF(COUNTIF($A$4:$A228,$A228)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A229=\"\",\"\",IF(COUNTIF($A$4:$A229,$A229)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A230=\"\",\"\",IF(COUNTIF($A$4:$A230,$A230)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A231=\"\",\"\",IF(COUNTIF($A$4:$A231,$A231)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A232=\"\",\"\",IF(COUNTIF($A$4:$A232,$A232)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A233=\"\",\"\",IF(COUNTIF($A$4:$A233,$A233)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A234=\"\",\"\",IF(COUNTIF($A$4:$A234,$A234)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A235=\"\",\"\",IF(COUNTIF($A$4:$A235,$A235)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A236=\"\",\"\",IF(COUNTIF($A$4:$A236,$A236)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A237=\"\",\"\",IF(COUNTIF($A$4:$A237,$A237)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A238=\"\",\"\",IF(COUNTIF($A$4:$A238,$A238)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A239=\"\",\"\",IF(COUNTIF($A$4:$A239,$A239)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A240=\"\",\"\",IF(COUNTIF($A$4:$A240,$A240)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A241=\"\",\"\",IF(COUNTIF($A$4:$A241,$A241)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A242=\"\",\"\",IF(COUNTIF($A$4:$A242,$A242)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A243=\"\",\"\",IF(COUNTIF($A$4:$A243,$A243)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A244=\"\",\"\",IF(COUNTIF($A$4:$A244,$A244)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A245=\"\",\"\",IF(COUNTIF($A$4:$A245,$A245)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A246=\"\",\"\",IF(COUNTIF($A$4:$A246,$A246)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A247=\"\",\"\",IF(COUNTIF($A$4:$A247,$A247)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A248=\"\",\"\",IF(COUNTIF($A$4:$A248,$A248)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A249=\"\",\"\",IF(COUNTIF($A$4:$A249,$A249)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A250=\"\",\"\",IF(COUNTIF($A$4:$A250,$A250)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A251=\"\",\"\",IF(COUNTIF($A$4:$A251,$A251)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A252=\"\",\"\",IF(COUNTIF($A$4:$A252,$A252)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A253=\"\",\"\",IF(COUNTIF($A$4:$A253,$A253)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A254=\"\",\"\",IF(COUNTIF($A$4:$A254,$A254)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A255=\"\",\"\",IF(COUNTIF($A$4:$A255,$A255)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A256=\"\",\"\",IF(COUNTIF($A$4:$A256,$A256)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A257=\"\",\"\",IF(COUNTIF($A$4:$A257,$A257)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A258=\"\",\"\",IF(COUNTIF($A$4:$A258,$A258)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A259=\"\",\"\",IF(COUNTIF($A$4:$A259,$A259)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A260=\"\",\"\",IF(COUNTIF($A$4:$A260,$A260)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A261=\"\",\"\",IF(COUNTIF($A$4:$A261,$A261)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A262=\"\",\"\",IF(COUNTIF($A$4:$A262,$A262)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A263=\"\",\"\",IF(COUNTIF($A$4:$A263,$A263)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A264=\"\",\"\",IF(COUNTIF($A$4:$A264,$A264)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A265=\"\",\"\",IF(COUNTIF($A$4:$A265,$A265)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A266=\"\",\"\",IF(COUNTIF($A$4:$A266,$A266)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A267=\"\",\"\",IF(COUNTIF($A$4:$A267,$A267)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A268=\"\",\"\",IF(COUNTIF($A$4:$A268,$A268)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A269=\"\",\"\",IF(COUNTIF($A$4:$A269,$A269)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A270=\"\",\"\",IF(COUNTIF($A$4:$A270,$A270)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A271=\"\",\"\",IF(COUNTIF($A$4:$A271,$A271)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A272=\"\",\"\",IF(COUNTIF($A$4:$A272,$A272)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A273=\"\",\"\",IF(COUNTIF($A$4:$A273,$A273)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A274=\"\",\"\",IF(COUNTIF($A$4:$A274,$A274)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A275=\"\",\"\",IF(COUNTIF($A$4:$A275,$A275)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A276=\"\",\"\",IF(COUNTIF($A$4:$A276,$A276)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A277=\"\",\"\",IF(COUNTIF($A$4:$A277,$A277)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A278=\"\",\"\",IF(COUNTIF($A$4:$A278,$A278)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A279=\"\",\"\",IF(COUNTIF($A$4:$A279,$A279)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A280=\"\",\"\",IF(COUNTIF($A$4:$A280,$A280)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A281=\"\",\"\",IF(COUNTIF($A$4:$A281,$A281)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A282=\"\",\"\",IF(COUNTIF($A$4:$A282,$A282)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A283=\"\",\"\",IF(COUNTIF($A$4:$A283,$A283)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A284=\"\",\"\",IF(COUNTIF($A$4:$A284,$A284)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A285=\"\",\"\",IF(COUNTIF($A$4:$A285,$A285)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A286=\"\",\"\",IF(COUNTIF($A$4:$A286,$A286)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A287=\"\",\"\",IF(COUNTIF($A$4:$A287,$A287)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A288=\"\",\"\",IF(COUNTIF($A$4:$A288,$A288)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A289=\"\",\"\",IF(COUNTIF($A$4:$A289,$A289)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A290=\"\",\"\",IF(COUNTIF($A$4:$A290,$A290)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A291=\"\",\"\",IF(COUNTIF($A$4:$A291,$A291)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A292=\"\",\"\",IF(COUNTIF($A$4:$A292,$A292)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A293=\"\",\"\",IF(COUNTIF($A$4:$A293,$A293)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A294=\"\",\"\",IF(COUNTIF($A$4:$A294,$A294)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A295=\"\",\"\",IF(COUNTIF($A$4:$A295,$A295)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A296=\"\",\"\",IF(COUNTIF($A$4:$A296,$A296)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A297=\"\",\"\",IF(COUNTIF($A$4:$A297,$A297)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A298=\"\",\"\",IF(COUNTIF($A$4:$A298,$A298)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A299=\"\",\"\",IF(COUNTIF($A$4:$A299,$A299)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A300=\"\",\"\",IF(COUNTIF($A$4:$A300,$A300)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A301=\"\",\"\",IF(COUNTIF($A$4:$A301,$A301)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A302=\"\",\"\",IF(COUNTIF($A$4:$A302,$A302)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A303=\"\",\"\",IF(COUNTIF($A$4:$A303,$A303)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A304=\"\",\"\",IF(COUNTIF($A$4:$A304,$A304)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A305=\"\",\"\",IF(COUNTIF($A$4:$A305,$A305)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A306=\"\",\"\",IF(COUNTIF($A$4:$A306,$A306)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A307=\"\",\"\",IF(COUNTIF($A$4:$A307,$A307)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A308=\"\",\"\",IF(COUNTIF($A$4:$A308,$A308)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A309=\"\",\"\",IF(COUNTIF($A$4:$A309,$A309)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A310=\"\",\"\",IF(COUNTIF($A$4:$A310,$A310)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A311=\"\",\"\",IF(COUNTIF($A$4:$A311,$A311)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A312=\"\",\"\",IF(COUNTIF($A$4:$A312,$A312)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A313=\"\",\"\",IF(COUNTIF($A$4:$A313,$A313)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A314=\"\",\"\",IF(COUNTIF($A$4:$A314,$A314)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A315=\"\",\"\",IF(COUNTIF($A$4:$A315,$A315)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A316=\"\",\"\",IF(COUNTIF($A$4:$A316,$A316)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A317=\"\",\"\",IF(COUNTIF($A$4:$A317,$A317)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A318=\"\",\"\",IF(COUNTIF($A$4:$A318,$A318)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A319=\"\",\"\",IF(COUNTIF($A$4:$A319,$A319)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A320=\"\",\"\",IF(COUNTIF($A$4:$A320,$A320)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A321=\"\",\"\",IF(COUNTIF($A$4:$A321,$A321)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A322=\"\",\"\",IF(COUNTIF($A$4:$A322,$A322)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A323=\"\",\"\",IF(COUNTIF($A$4:$A323,$A323)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A324=\"\",\"\",IF(COUNTIF($A$4:$A324,$A324)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A325=\"\",\"\",IF(COUNTIF($A$4:$A325,$A325)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A326=\"\",\"\",IF(COUNTIF($A$4:$A326,$A326)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A327=\"\",\"\",IF(COUNTIF($A$4:$A327,$A327)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A328=\"\",\"\",IF(COUNTIF($A$4:$A328,$A328)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A329=\"\",\"\",IF(COUNTIF($A$4:$A329,$A329)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A330=\"\",\"\",IF(COUNTIF($A$4:$A330,$A330)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A331=\"\",\"\",IF(COUNTIF($A$4:$A331,$A331)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A332=\"\",\"\",IF(COUNTIF($A$4:$A332,$A332)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A333=\"\",\"\",IF(COUNTIF($A$4:$A333,$A333)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A334=\"\",\"\",IF(COUNTIF($A$4:$A334,$A334)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A335=\"\",\"\",IF(COUNTIF($A$4:$A335,$A335)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A336=\"\",\"\",IF(COUNTIF($A$4:$A336,$A336)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A337=\"\",\"\",IF(COUNTIF($A$4:$A337,$A337)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A338=\"\",\"\",IF(COUNTIF($A$4:$A338,$A338)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A339=\"\",\"\",IF(COUNTIF($A$4:$A339,$A339)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A340=\"\",\"\",IF(COUNTIF($A$4:$A340,$A340)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A341=\"\",\"\",IF(COUNTIF($A$4:$A341,$A341)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A342=\"\",\"\",IF(COUNTIF($A$4:$A342,$A342)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A343=\"\",\"\",IF(COUNTIF($A$4:$A343,$A343)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A344=\"\",\"\",IF(COUNTIF($A$4:$A344,$A344)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A345=\"\",\"\",IF(COUNTIF($A$4:$A345,$A345)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A346=\"\",\"\",IF(COUNTIF($A$4:$A346,$A346)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A347=\"\",\"\",IF(COUNTIF($A$4:$A347,$A347)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A348=\"\",\"\",IF(COUNTIF($A$4:$A348,$A348)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A349=\"\",\"\",IF(COUNTIF($A$4:$A349,$A349)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A350=\"\",\"\",IF(COUNTIF($A$4:$A350,$A350)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A351=\"\",\"\",IF(COUNTIF($A$4:$A351,$A351)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A352=\"\",\"\",IF(COUNTIF($A$4:$A352,$A352)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A353=\"\",\"\",IF(COUNTIF($A$4:$A353,$A353)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A354=\"\",\"\",IF(COUNTIF($A$4:$A354,$A354)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A355=\"\",\"\",IF(COUNTIF($A$4:$A355,$A355)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A356=\"\",\"\",IF(COUNTIF($A$4:$A356,$A356)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A357=\"\",\"\",IF(COUNTIF($A$4:$A357,$A357)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A358=\"\",\"\",IF(COUNTIF($A$4:$A358,$A358)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A359=\"\",\"\",IF(COUNTIF($A$4:$A359,$A359)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A360=\"\",\"\",IF(COUNTIF($A$4:$A360,$A360)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A361=\"\",\"\",IF(COUNTIF($A$4:$A361,$A361)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A362=\"\",\"\",IF(COUNTIF($A$4:$A362,$A362)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A363=\"\",\"\",IF(COUNTIF($A$4:$A363,$A363)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A364=\"\",\"\",IF(COUNTIF($A$4:$A364,$A364)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A365=\"\",\"\",IF(COUNTIF($A$4:$A365,$A365)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A366=\"\",\"\",IF(COUNTIF($A$4:$A366,$A366)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A367=\"\",\"\",IF(COUNTIF($A$4:$A367,$A367)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A368=\"\",\"\",IF(COUNTIF($A$4:$A368,$A368)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A369=\"\",\"\",IF(COUNTIF($A$4:$A369,$A369)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A370=\"\",\"\",IF(COUNTIF($A$4:$A370,$A370)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A371=\"\",\"\",IF(COUNTIF($A$4:$A371,$A371)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A372=\"\",\"\",IF(COUNTIF($A$4:$A372,$A372)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A373=\"\",\"\",IF(COUNTIF($A$4:$A373,$A373)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A374=\"\",\"\",IF(COUNTIF($A$4:$A374,$A374)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A375=\"\",\"\",IF(COUNTIF($A$4:$A375,$A375)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A376=\"\",\"\",IF(COUNTIF($A$4:$A376,$A376)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A377=\"\",\"\",IF(COUNTIF($A$4:$A377,$A377)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A378=\"\",\"\",IF(COUNTIF($A$4:$A378,$A378)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A379=\"\",\"\",IF(COUNTIF($A$4:$A379,$A379)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A380=\"\",\"\",IF(COUNTIF($A$4:$A380,$A380)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A381=\"\",\"\",IF(COUNTIF($A$4:$A381,$A381)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A382=\"\",\"\",IF(COUNTIF($A$4:$A382,$A382)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A383=\"\",\"\",IF(COUNTIF($A$4:$A383,$A383)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A384=\"\",\"\",IF(COUNTIF($A$4:$A384,$A384)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A385=\"\",\"\",IF(COUNTIF($A$4:$A385,$A385)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A386=\"\",\"\",IF(COUNTIF($A$4:$A386,$A386)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A387=\"\",\"\",IF(COUNTIF($A$4:$A387,$A387)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A388=\"\",\"\",IF(COUNTIF($A$4:$A388,$A388)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A389=\"\",\"\",IF(COUNTIF($A$4:$A389,$A389)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A390=\"\",\"\",IF(COUNTIF($A$4:$A390,$A390)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A391=\"\",\"\",IF(COUNTIF($A$4:$A391,$A391)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A392=\"\",\"\",IF(COUNTIF($A$4:$A392,$A392)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A393=\"\",\"\",IF(COUNTIF($A$4:$A393,$A393)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A394=\"\",\"\",IF(COUNTIF($A$4:$A394,$A394)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A395=\"\",\"\",IF(COUNTIF($A$4:$A395,$A395)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A396=\"\",\"\",IF(COUNTIF($A$4:$A396,$A396)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A397=\"\",\"\",IF(COUNTIF($A$4:$A397,$A397)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A398=\"\",\"\",IF(COUNTIF($A$4:$A398,$A398)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A399=\"\",\"\",IF(COUNTIF($A$4:$A399,$A399)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A400=\"\",\"\",IF(COUNTIF($A$4:$A400,$A400)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A401=\"\",\"\",IF(COUNTIF($A$4:$A401,$A401)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A402=\"\",\"\",IF(COUNTIF($A$4:$A402,$A402)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A403=\"\",\"\",IF(COUNTIF($A$4:$A403,$A403)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A404=\"\",\"\",IF(COUNTIF($A$4:$A404,$A404)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A405=\"\",\"\",IF(COUNTIF($A$4:$A405,$A405)=1,1,0))","v":0}]
[{"$nulls":7},{"$f":"IF($A406=\"\",\"\",IF(COUNTIF($A$4:$A406,$A406)=1,1,0))","v":0}]

{"sheet":"WBS_Livrables","index":3,"n_rows":8,"n_cols":9,"rows_kept":8}
["WBS Livrables & Jalons"]
[]
["ID Livrable","Nom","Type","Date prévue","Date réelle","Statut","Dépendances","RACI","Propriétaire"]
["LIV-001","Plan Qualité Projet (PQP)","Document","2025-08-05","2025-08-04","Livré",null,"R","Resp Qualité"]
["LIV-002","Plan de Contrôle Ligne A","Document","2025-08-12",null,"En cours","LIV-001","A","Resp Méthodes"]
["LIV-003","Procédure Traçabilité","Document","2025-08-18",null,"Ouvert","LIV-001","C","Resp Méthodes"]
["LIV-004","Rapport Essais FPY","Rapport","2025-09-05",null,"Ouvert","LIV-002","I","Resp Prod"]
["LIV-005","Certification CE","Certificat","2025-09-20",null,"Ouvert","LIV-002","A","HSE"]

{"sheet":"Essais_Validation","index":4,"n_rows":7,"n_cols":8,"rows_kept":7}
["Plan d'Essais & Validation"]
[]
["ID Essai","Exigence liée","Type","Résultat","Commentaire","Rapport","Pilote","Date"]
["TEST-001","REQ-001","Dimensionnel","OK","Défaut mineur","RPT-001","Resp Qualité","2025-08-10"]
["TEST-002","REQ-001","Fonctionnel","NOK","Jeu hors tol.","RPT-002","Resp Qualité","2025-08-12"]
["TEST-FPY-01","REQ-003","Performance","En cours",null,null,"Resp Prod"]
["TEST-LD-01","REQ-008","Fiabilité","Planifié",null,null,"R&D"]

{"sheet":"Actions_CAPA","index":5,"n_rows":6,"n_cols":8,"rows_kept":6}
["Actions / CAPA"]
[]
["ID Action","Description","Domaine","Responsable","Échéance","Statut","Date clôture","Lien Exigence"]
["ACT-001","Recaler gabarit contrôle Ligne A","Qualité","Resp Qualité","2025-08-15","Ouverte",null,"REQ-001"]
["ACT-002","Finaliser procédure traçabilité","Méthodes","Resp Méthodes","2025-08-14","En cours",null,"REQ-002"]
["ACT-003","Former opérateurs mesure 3D","Qualité","Resp Qualité","2025-08-25","Planifiée",null,"REQ-001"]

{"sheet":"Risque_Qualite","index":6,"n_rows":5,"n_cols":10,"rows_kept":5}
["Risques Qualité (PFMEA light)"]
[]
["ID Risque","Description","Type","Gravité(1-5)","Occurrence(1-5)","Détection(1-5)","RPN","Action prévue","Propriétaire","Statut"]
["R-001","Erreur de réglage gabarit","Process","4","3","3","36","Action de calibration hebdo","Resp Méthodes","Ouvert"]
["R-002","Mauvaise traçabilité lot","Process","5","2","3","30","Audit terrain + QR code","Resp Méthodes","Ouvert"]

{"sheet":"Timeline","index":7,"n_rows":203,"n_cols":7,"rows_kept":203}
["Timeline (Gantt)"]
[]
["ID Tâche","Tâche","Début","Fin","% Avancement","Début_num","Durée"]
["T-001","Rédaction PQP","2025-08-01","2025-08-05",100,{"$f":"IF(C4=\"\",\"\",C4)","v":0},{"$f":"IF(OR(C4=\"\",D4=\"\"),\"\",D4-C4+1)","v":0}]
["T-002","Procédures Traçabilité","2025-08-06","2025-08-18",40,{"$f":"IF(C5=\"\",\"\",C5)","v":0},{"$f":"IF(OR(C5=\"\",D5=\"\"),\"\",D5-C5+1)","v":0}]
["T-003","Plan de Contrôle Ligne A","2025-08-08","2025-08-12",60,{"$f":"IF(C6=\"\",\"\",C6)","v":0},{"$f":"IF(OR(C6=\"\",D6=\"\"),\"\",D6-C6+1)","v":0}]
["T-004","Essais FPY","2025-08-20","2025-09-05",15,{"$f":"IF(C7=\"\",\"\",C7)","v":0},{"$f":"IF(OR(C7=\"\",D7=\"\"),\"\",D7-C7+1)","v":0}]
["T-005","Certification CE","2025-09-06","2025-09-20",0,{"$f":"IF(C8=\"\",\"\",C8)","v":0},{"$f":"IF(OR(C8=\"\",D8=\"\"),\"\",D8-C8+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C9=\"\",\"\",C9)","v":0},{"$f":"IF(OR(C9=\"\",D9=\"\"),\"\",D9-C9+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C10=\"\",\"\",C10)","v":0},{"$f":"IF(OR(C10=\"\",D10=\"\"),\"\",D10-C10+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C11=\"\",\"\",C11)","v":0},{"$f":"IF(OR(C11=\"\",D11=\"\"),\"\",D11-C11+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C12=\"\",\"\",C12)","v":0},{"$f":"IF(OR(C12=\"\",D12=\"\"),\"\",D12-C12+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C13=\"\",\"\",C13)","v":0},{"$f":"IF(OR(C13=\"\",D13=\"\"),\"\",D13-C13+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C14=\"\",\"\",C14)","v":0},{"$f":"IF(OR(C14=\"\",D14=\"\"),\"\",D14-C14+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C15=\"\",\"\",C15)","v":0},{"$f":"IF(OR(C15=\"\",D15=\"\"),\"\",D15-C15+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C16=\"\",\"\",C16)","v":0},{"$f":"IF(OR(C16=\"\",D16=\"\"),\"\",D16-C16+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C17=\"\",\"\",C17)","v":0},{"$f":"IF(OR(C17=\"\",D17=\"\"),\"\",D17-C17+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C18=\"\",\"\",C18)","v":0},{"$f":"IF(OR(C18=\"\",D18=\"\"),\"\",D18-C18+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C19=\"\",\"\",C19)","v":0},{"$f":"IF(OR(C19=\"\",D19=\"\"),\"\",D19-C19+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C20=\"\",\"\",C20)","v":0},{"$f":"IF(OR(C20=\"\",D20=\"\"),\"\",D20-C20+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C21=\"\",\"\",C21)","v":0},{"$f":"IF(OR(C21=\"\",D21=\"\"),\"\",D21-C21+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C22=\"\",\"\",C22)","v":0},{"$f":"IF(OR(C22=\"\",D22=\"\"),\"\",D22-C22+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C23=\"\",\"\",C23)","v":0},{"$f":"IF(OR(C23=\"\",D23=\"\"),\"\",D23-C23+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C24=\"\",\"\",C24)","v":0},{"$f":"IF(OR(C24=\"\",D24=\"\"),\"\",D24-C24+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C25=\"\",\"\",C25)","v":0},{"$f":"IF(OR(C25=\"\",D25=\"\"),\"\",D25-C25+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C26=\"\",\"\",C26)","v":0},{"$f":"IF(OR(C26=\"\",D26=\"\"),\"\",D26-C26+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C27=\"\",\"\",C27)","v":0},{"$f":"IF(OR(C27=\"\",D27=\"\"),\"\",D27-C27+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C28=\"\",\"\",C28)","v":0},{"$f":"IF(OR(C28=\"\",D28=\"\"),\"\",D28-C28+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C29=\"\",\"\",C29)","v":0},{"$f":"IF(OR(C29=\"\",D29=\"\"),\"\",D29-C29+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C30=\"\",\"\",C30)","v":0},{"$f":"IF(OR(C30=\"\",D30=\"\"),\"\",D30-C30+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C31=\"\",\"\",C31)","v":0},{"$f":"IF(OR(C31=\"\",D31=\"\"),\"\",D31-C31+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C32=\"\",\"\",C32)","v":0},{"$f":"IF(OR(C32=\"\",D32=\"\"),\"\",D32-C32+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C33=\"\",\"\",C33)","v":0},{"$f":"IF(OR(C33=\"\",D33=\"\"),\"\",D33-C33+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C34=\"\",\"\",C34)","v":0},{"$f":"IF(OR(C34=\"\",D34=\"\"),\"\",D34-C34+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C35=\"\",\"\",C35)","v":0},{"$f":"IF(OR(C35=\"\",D35=\"\"),\"\",D35-C35+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C36=\"\",\"\",C36)","v":0},{"$f":"IF(OR(C36=\"\",D36=\"\"),\"\",D36-C36+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C37=\"\",\"\",C37)","v":0},{"$f":"IF(OR(C37=\"\",D37=\"\"),\"\",D37-C37+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C38=\"\",\"\",C38)","v":0},{"$f":"IF(OR(C38=\"\",D38=\"\"),\"\",D38-C38+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C39=\"\",\"\",C39)","v":0},{"$f":"IF(OR(C39=\"\",D39=\"\"),\"\",D39-C39+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C40=\"\",\"\",C40)","v":0},{"$f":"IF(OR(C40=\"\",D40=\"\"),\"\",D40-C40+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C41=\"\",\"\",C41)","v":0},{"$f":"IF(OR(C41=\"\",D41=\"\"),\"\",D41-C41+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C42=\"\",\"\",C42)","v":0},{"$f":"IF(OR(C42=\"\",D42=\"\"),\"\",D42-C42+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C43=\"\",\"\",C43)","v":0},{"$f":"IF(OR(C43=\"\",D43=\"\"),\"\",D43-C43+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C44=\"\",\"\",C44)","v":0},{"$f":"IF(OR(C44=\"\",D44=\"\"),\"\",D44-C44+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C45=\"\",\"\",C45)","v":0},{"$f":"IF(OR(C45=\"\",D45=\"\"),\"\",D45-C45+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C46=\"\",\"\",C46)","v":0},{"$f":"IF(OR(C46=\"\",D46=\"\"),\"\",D46-C46+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C47=\"\",\"\",C47)","v":0},{"$f":"IF(OR(C47=\"\",D47=\"\"),\"\",D47-C47+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C48=\"\",\"\",C48)","v":0},{"$f":"IF(OR(C48=\"\",D48=\"\"),\"\",D48-C48+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C49=\"\",\"\",C49)","v":0},{"$f":"IF(OR(C49=\"\",D49=\"\"),\"\",D49-C49+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C50=\"\",\"\",C50)","v":0},{"$f":"IF(OR(C50=\"\",D50=\"\"),\"\",D50-C50+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C51=\"\",\"\",C51)","v":0},{"$f":"IF(OR(C51=\"\",D51=\"\"),\"\",D51-C51+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C52=\"\",\"\",C52)","v":0},{"$f":"IF(OR(C52=\"\",D52=\"\"),\"\",D52-C52+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C53=\"\",\"\",C53)","v":0},{"$f":"IF(OR(C53=\"\",D53=\"\"),\"\",D53-C53+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C54=\"\",\"\",C54)","v":0},{"$f":"IF(OR(C54=\"\",D54=\"\"),\"\",D54-C54+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C55=\"\",\"\",C55)","v":0},{"$f":"IF(OR(C55=\"\",D55=\"\"),\"\",D55-C55+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C56=\"\",\"\",C56)","v":0},{"$f":"IF(OR(C56=\"\",D56=\"\"),\"\",D56-C56+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C57=\"\",\"\",C57)","v":0},{"$f":"IF(OR(C57=\"\",D57=\"\"),\"\",D57-C57+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C58=\"\",\"\",C58)","v":0},{"$f":"IF(OR(C58=\"\",D58=\"\"),\"\",D58-C58+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C59=\"\",\"\",C59)","v":0},{"$f":"IF(OR(C59=\"\",D59=\"\"),\"\",D59-C59+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C60=\"\",\"\",C60)","v":0},{"$f":"IF(OR(C60=\"\",D60=\"\"),\"\",D60-C60+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C61=\"\",\"\",C61)","v":0},{"$f":"IF(OR(C61=\"\",D61=\"\"),\"\",D61-C61+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C62=\"\",\"\",C62)","v":0},{"$f":"IF(OR(C62=\"\",D62=\"\"),\"\",D62-C62+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C63=\"\",\"\",C63)","v":0},{"$f":"IF(OR(C63=\"\",D63=\"\"),\"\",D63-C63+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C64=\"\",\"\",C64)","v":0},{"$f":"IF(OR(C64=\"\",D64=\"\"),\"\",D64-C64+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C65=\"\",\"\",C65)","v":0},{"$f":"IF(OR(C65=\"\",D65=\"\"),\"\",D65-C65+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C66=\"\",\"\",C66)","v":0},{"$f":"IF(OR(C66=\"\",D66=\"\"),\"\",D66-C66+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C67=\"\",\"\",C67)","v":0},{"$f":"IF(OR(C67=\"\",D67=\"\"),\"\",D67-C67+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C68=\"\",\"\",C68)","v":0},{"$f":"IF(OR(C68=\"\",D68=\"\"),\"\",D68-C68+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C69=\"\",\"\",C69)","v":0},{"$f":"IF(OR(C69=\"\",D69=\"\"),\"\",D69-C69+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C70=\"\",\"\",C70)","v":0},{"$f":"IF(OR(C70=\"\",D70=\"\"),\"\",D70-C70+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C71=\"\",\"\",C71)","v":0},{"$f":"IF(OR(C71=\"\",D71=\"\"),\"\",D71-C71+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C72=\"\",\"\",C72)","v":0},{"$f":"IF(OR(C72=\"\",D72=\"\"),\"\",D72-C72+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C73=\"\",\"\",C73)","v":0},{"$f":"IF(OR(C73=\"\",D73=\"\"),\"\",D73-C73+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C74=\"\",\"\",C74)","v":0},{"$f":"IF(OR(C74=\"\",D74=\"\"),\"\",D74-C74+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C75=\"\",\"\",C75)","v":0},{"$f":"IF(OR(C75=\"\",D75=\"\"),\"\",D75-C75+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C76=\"\",\"\",C76)","v":0},{"$f":"IF(OR(C76=\"\",D76=\"\"),\"\",D76-C76+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C77=\"\",\"\",C77)","v":0},{"$f":"IF(OR(C77=\"\",D77=\"\"),\"\",D77-C77+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C78=\"\",\"\",C78)","v":0},{"$f":"IF(OR(C78=\"\",D78=\"\"),\"\",D78-C78+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C79=\"\",\"\",C79)","v":0},{"$f":"IF(OR(C79=\"\",D79=\"\"),\"\",D79-C79+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C80=\"\",\"\",C80)","v":0},{"$f":"IF(OR(C80=\"\",D80=\"\"),\"\",D80-C80+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C81=\"\",\"\",C81)","v":0},{"$f":"IF(OR(C81=\"\",D81=\"\"),\"\",D81-C81+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C82=\"\",\"\",C82)","v":0},{"$f":"IF(OR(C82=\"\",D82=\"\"),\"\",D82-C82+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C83=\"\",\"\",C83)","v":0},{"$f":"IF(OR(C83=\"\",D83=\"\"),\"\",D83-C83+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C84=\"\",\"\",C84)","v":0},{"$f":"IF(OR(C84=\"\",D84=\"\"),\"\",D84-C84+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C85=\"\",\"\",C85)","v":0},{"$f":"IF(OR(C85=\"\",D85=\"\"),\"\",D85-C85+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C86=\"\",\"\",C86)","v":0},{"$f":"IF(OR(C86=\"\",D86=\"\"),\"\",D86-C86+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C87=\"\",\"\",C87)","v":0},{"$f":"IF(OR(C87=\"\",D87=\"\"),\"\",D87-C87+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C88=\"\",\"\",C88)","v":0},{"$f":"IF(OR(C88=\"\",D88=\"\"),\"\",D88-C88+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C89=\"\",\"\",C89)","v":0},{"$f":"IF(OR(C89=\"\",D89=\"\"),\"\",D89-C89+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C90=\"\",\"\",C90)","v":0},{"$f":"IF(OR(C90=\"\",D90=\"\"),\"\",D90-C90+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C91=\"\",\"\",C91)","v":0},{"$f":"IF(OR(C91=\"\",D91=\"\"),\"\",D91-C91+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C92=\"\",\"\",C92)","v":0},{"$f":"IF(OR(C92=\"\",D92=\"\"),\"\",D92-C92+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C93=\"\",\"\",C93)","v":0},{"$f":"IF(OR(C93=\"\",D93=\"\"),\"\",D93-C93+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C94=\"\",\"\",C94)","v":0},{"$f":"IF(OR(C94=\"\",D94=\"\"),\"\",D94-C94+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C95=\"\",\"\",C95)","v":0},{"$f":"IF(OR(C95=\"\",D95=\"\"),\"\",D95-C95+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C96=\"\",\"\",C96)","v":0},{"$f":"IF(OR(C96=\"\",D96=\"\"),\"\",D96-C96+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C97=\"\",\"\",C97)","v":0},{"$f":"IF(OR(C97=\"\",D97=\"\"),\"\",D97-C97+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C98=\"\",\"\",C98)","v":0},{"$f":"IF(OR(C98=\"\",D98=\"\"),\"\",D98-C98+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C99=\"\",\"\",C99)","v":0},{"$f":"IF(OR(C99=\"\",D99=\"\"),\"\",D99-C99+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C100=\"\",\"\",C100)","v":0},{"$f":"IF(OR(C100=\"\",D100=\"\"),\"\",D100-C100+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C101=\"\",\"\",C101)","v":0},{"$f":"IF(OR(C101=\"\",D101=\"\"),\"\",D101-C101+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C102=\"\",\"\",C102)","v":0},{"$f":"IF(OR(C102=\"\",D102=\"\"),\"\",D102-C102+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C103=\"\",\"\",C103)","v":0},{"$f":"IF(OR(C103=\"\",D103=\"\"),\"\",D103-C103+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C104=\"\",\"\",C104)","v":0},{"$f":"IF(OR(C104=\"\",D104=\"\"),\"\",D104-C104+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C105=\"\",\"\",C105)","v":0},{"$f":"IF(OR(C105=\"\",D105=\"\"),\"\",D105-C105+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C106=\"\",\"\",C106)","v":0},{"$f":"IF(OR(C106=\"\",D106=\"\"),\"\",D106-C106+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C107=\"\",\"\",C107)","v":0},{"$f":"IF(OR(C107=\"\",D107=\"\"),\"\",D107-C107+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C108=\"\",\"\",C108)","v":0},{"$f":"IF(OR(C108=\"\",D108=\"\"),\"\",D108-C108+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C109=\"\",\"\",C109)","v":0},{"$f":"IF(OR(C109=\"\",D109=\"\"),\"\",D109-C109+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C110=\"\",\"\",C110)","v":0},{"$f":"IF(OR(C110=\"\",D110=\"\"),\"\",D110-C110+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C111=\"\",\"\",C111)","v":0},{"$f":"IF(OR(C111=\"\",D111=\"\"),\"\",D111-C111+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C112=\"\",\"\",C112)","v":0},{"$f":"IF(OR(C112=\"\",D112=\"\"),\"\",D112-C112+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C113=\"\",\"\",C113)","v":0},{"$f":"IF(OR(C113=\"\",D113=\"\"),\"\",D113-C113+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C114=\"\",\"\",C114)","v":0},{"$f":"IF(OR(C114=\"\",D114=\"\"),\"\",D114-C114+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C115=\"\",\"\",C115)","v":0},{"$f":"IF(OR(C115=\"\",D115=\"\"),\"\",D115-C115+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C116=\"\",\"\",C116)","v":0},{"$f":"IF(OR(C116=\"\",D116=\"\"),\"\",D116-C116+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C117=\"\",\"\",C117)","v":0},{"$f":"IF(OR(C117=\"\",D117=\"\"),\"\",D117-C117+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C118=\"\",\"\",C118)","v":0},{"$f":"IF(OR(C118=\"\",D118=\"\"),\"\",D118-C118+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C119=\"\",\"\",C119)","v":0},{"$f":"IF(OR(C119=\"\",D119=\"\"),\"\",D119-C119+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C120=\"\",\"\",C120)","v":0},{"$f":"IF(OR(C120=\"\",D120=\"\"),\"\",D120-C120+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C121=\"\",\"\",C121)","v":0},{"$f":"IF(OR(C121=\"\",D121=\"\"),\"\",D121-C121+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C122=\"\",\"\",C122)","v":0},{"$f":"IF(OR(C122=\"\",D122=\"\"),\"\",D122-C122+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C123=\"\",\"\",C123)","v":0},{"$f":"IF(OR(C123=\"\",D123=\"\"),\"\",D123-C123+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C124=\"\",\"\",C124)","v":0},{"$f":"IF(OR(C124=\"\",D124=\"\"),\"\",D124-C124+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C125=\"\",\"\",C125)","v":0},{"$f":"IF(OR(C125=\"\",D125=\"\"),\"\",D125-C125+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C126=\"\",\"\",C126)","v":0},{"$f":"IF(OR(C126=\"\",D126=\"\"),\"\",D126-C126+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C127=\"\",\"\",C127)","v":0},{"$f":"IF(OR(C127=\"\",D127=\"\"),\"\",D127-C127+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C128=\"\",\"\",C128)","v":0},{"$f":"IF(OR(C128=\"\",D128=\"\"),\"\",D128-C128+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C129=\"\",\"\",C129)","v":0},{"$f":"IF(OR(C129=\"\",D129=\"\"),\"\",D129-C129+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C130=\"\",\"\",C130)","v":0},{"$f":"IF(OR(C130=\"\",D130=\"\"),\"\",D130-C130+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C131=\"\",\"\",C131)","v":0},{"$f":"IF(OR(C131=\"\",D131=\"\"),\"\",D131-C131+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C132=\"\",\"\",C132)","v":0},{"$f":"IF(OR(C132=\"\",D132=\"\"),\"\",D132-C132+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C133=\"\",\"\",C133)","v":0},{"$f":"IF(OR(C133=\"\",D133=\"\"),\"\",D133-C133+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C134=\"\",\"\",C134)","v":0},{"$f":"IF(OR(C134=\"\",D134=\"\"),\"\",D134-C134+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C135=\"\",\"\",C135)","v":0},{"$f":"IF(OR(C135=\"\",D135=\"\"),\"\",D135-C135+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C136=\"\",\"\",C136)","v":0},{"$f":"IF(OR(C136=\"\",D136=\"\"),\"\",D136-C136+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C137=\"\",\"\",C137)","v":0},{"$f":"IF(OR(C137=\"\",D137=\"\"),\"\",D137-C137+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C138=\"\",\"\",C138)","v":0},{"$f":"IF(OR(C138=\"\",D138=\"\"),\"\",D138-C138+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C139=\"\",\"\",C139)","v":0},{"$f":"IF(OR(C139=\"\",D139=\"\"),\"\",D139-C139+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C140=\"\",\"\",C140)","v":0},{"$f":"IF(OR(C140=\"\",D140=\"\"),\"\",D140-C140+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C141=\"\",\"\",C141)","v":0},{"$f":"IF(OR(C141=\"\",D141=\"\"),\"\",D141-C141+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C142=\"\",\"\",C142)","v":0},{"$f":"IF(OR(C142=\"\",D142=\"\"),\"\",D142-C142+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C143=\"\",\"\",C143)","v":0},{"$f":"IF(OR(C143=\"\",D143=\"\"),\"\",D143-C143+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C144=\"\",\"\",C144)","v":0},{"$f":"IF(OR(C144=\"\",D144=\"\"),\"\",D144-C144+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C145=\"\",\"\",C145)","v":0},{"$f":"IF(OR(C145=\"\",D145=\"\"),\"\",D145-C145+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C146=\"\",\"\",C146)","v":0},{"$f":"IF(OR(C146=\"\",D146=\"\"),\"\",D146-C146+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C147=\"\",\"\",C147)","v":0},{"$f":"IF(OR(C147=\"\",D147=\"\"),\"\",D147-C147+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C148=\"\",\"\",C148)","v":0},{"$f":"IF(OR(C148=\"\",D148=\"\"),\"\",D148-C148+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C149=\"\",\"\",C149)","v":0},{"$f":"IF(OR(C149=\"\",D149=\"\"),\"\",D149-C149+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C150=\"\",\"\",C150)","v":0},{"$f":"IF(OR(C150=\"\",D150=\"\"),\"\",D150-C150+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C151=\"\",\"\",C151)","v":0},{"$f":"IF(OR(C151=\"\",D151=\"\"),\"\",D151-C151+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C152=\"\",\"\",C152)","v":0},{"$f":"IF(OR(C152=\"\",D152=\"\"),\"\",D152-C152+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C153=\"\",\"\",C153)","v":0},{"$f":"IF(OR(C153=\"\",D153=\"\"),\"\",D153-C153+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C154=\"\",\"\",C154)","v":0},{"$f":"IF(OR(C154=\"\",D154=\"\"),\"\",D154-C154+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C155=\"\",\"\",C155)","v":0},{"$f":"IF(OR(C155=\"\",D155=\"\"),\"\",D155-C155+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C156=\"\",\"\",C156)","v":0},{"$f":"IF(OR(C156=\"\",D156=\"\"),\"\",D156-C156+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C157=\"\",\"\",C157)","v":0},{"$f":"IF(OR(C157=\"\",D157=\"\"),\"\",D157-C157+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C158=\"\",\"\",C158)","v":0},{"$f":"IF(OR(C158=\"\",D158=\"\"),\"\",D158-C158+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C159=\"\",\"\",C159)","v":0},{"$f":"IF(OR(C159=\"\",D159=\"\"),\"\",D159-C159+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C160=\"\",\"\",C160)","v":0},{"$f":"IF(OR(C160=\"\",D160=\"\"),\"\",D160-C160+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C161=\"\",\"\",C161)","v":0},{"$f":"IF(OR(C161=\"\",D161=\"\"),\"\",D161-C161+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C162=\"\",\"\",C162)","v":0},{"$f":"IF(OR(C162=\"\",D162=\"\"),\"\",D162-C162+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C163=\"\",\"\",C163)","v":0},{"$f":"IF(OR(C163=\"\",D163=\"\"),\"\",D163-C163+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C164=\"\",\"\",C164)","v":0},{"$f":"IF(OR(C164=\"\",D164=\"\"),\"\",D164-C164+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C165=\"\",\"\",C165)","v":0},{"$f":"IF(OR(C165=\"\",D165=\"\"),\"\",D165-C165+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C166=\"\",\"\",C166)","v":0},{"$f":"IF(OR(C166=\"\",D166=\"\"),\"\",D166-C166+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C167=\"\",\"\",C167)","v":0},{"$f":"IF(OR(C167=\"\",D167=\"\"),\"\",D167-C167+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C168=\"\",\"\",C168)","v":0},{"$f":"IF(OR(C168=\"\",D168=\"\"),\"\",D168-C168+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C169=\"\",\"\",C169)","v":0},{"$f":"IF(OR(C169=\"\",D169=\"\"),\"\",D169-C169+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C170=\"\",\"\",C170)","v":0},{"$f":"IF(OR(C170=\"\",D170=\"\"),\"\",D170-C170+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C171=\"\",\"\",C171)","v":0},{"$f":"IF(OR(C171=\"\",D171=\"\"),\"\",D171-C171+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C172=\"\",\"\",C172)","v":0},{"$f":"IF(OR(C172=\"\",D172=\"\"),\"\",D172-C172+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C173=\"\",\"\",C173)","v":0},{"$f":"IF(OR(C173=\"\",D173=\"\"),\"\",D173-C173+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C174=\"\",\"\",C174)","v":0},{"$f":"IF(OR(C174=\"\",D174=\"\"),\"\",D174-C174+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C175=\"\",\"\",C175)","v":0},{"$f":"IF(OR(C175=\"\",D175=\"\"),\"\",D175-C175+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C176=\"\",\"\",C176)","v":0},{"$f":"IF(OR(C176=\"\",D176=\"\"),\"\",D176-C176+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C177=\"\",\"\",C177)","v":0},{"$f":"IF(OR(C177=\"\",D177=\"\"),\"\",D177-C177+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C178=\"\",\"\",C178)","v":0},{"$f":"IF(OR(C178=\"\",D178=\"\"),\"\",D178-C178+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C179=\"\",\"\",C179)","v":0},{"$f":"IF(OR(C179=\"\",D179=\"\"),\"\",D179-C179+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C180=\"\",\"\",C180)","v":0},{"$f":"IF(OR(C180=\"\",D180=\"\"),\"\",D180-C180+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C181=\"\",\"\",C181)","v":0},{"$f":"IF(OR(C181=\"\",D181=\"\"),\"\",D181-C181+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C182=\"\",\"\",C182)","v":0},{"$f":"IF(OR(C182=\"\",D182=\"\"),\"\",D182-C182+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C183=\"\",\"\",C183)","v":0},{"$f":"IF(OR(C183=\"\",D183=\"\"),\"\",D183-C183+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C184=\"\",\"\",C184)","v":0},{"$f":"IF(OR(C184=\"\",D184=\"\"),\"\",D184-C184+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C185=\"\",\"\",C185)","v":0},{"$f":"IF(OR(C185=\"\",D185=\"\"),\"\",D185-C185+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C186=\"\",\"\",C186)","v":0},{"$f":"IF(OR(C186=\"\",D186=\"\"),\"\",D186-C186+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C187=\"\",\"\",C187)","v":0},{"$f":"IF(OR(C187=\"\",D187=\"\"),\"\",D187-C187+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C188=\"\",\"\",C188)","v":0},{"$f":"IF(OR(C188=\"\",D188=\"\"),\"\",D188-C188+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C189=\"\",\"\",C189)","v":0},{"$f":"IF(OR(C189=\"\",D189=\"\"),\"\",D189-C189+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C190=\"\",\"\",C190)","v":0},{"$f":"IF(OR(C190=\"\",D190=\"\"),\"\",D190-C190+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C191=\"\",\"\",C191)","v":0},{"$f":"IF(OR(C191=\"\",D191=\"\"),\"\",D191-C191+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C192=\"\",\"\",C192)","v":0},{"$f":"IF(OR(C192=\"\",D192=\"\"),\"\",D192-C192+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C193=\"\",\"\",C193)","v":0},{"$f":"IF(OR(C193=\"\",D193=\"\"),\"\",D193-C193+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C194=\"\",\"\",C194)","v":0},{"$f":"IF(OR(C194=\"\",D194=\"\"),\"\",D194-C194+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C195=\"\",\"\",C195)","v":0},{"$f":"IF(OR(C195=\"\",D195=\"\"),\"\",D195-C195+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C196=\"\",\"\",C196)","v":0},{"$f":"IF(OR(C196=\"\",D196=\"\"),\"\",D196-C196+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C197=\"\",\"\",C197)","v":0},{"$f":"IF(OR(C197=\"\",D197=\"\"),\"\",D197-C197+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C198=\"\",\"\",C198)","v":0},{"$f":"IF(OR(C198=\"\",D198=\"\"),\"\",D198-C198+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C199=\"\",\"\",C199)","v":0},{"$f":"IF(OR(C199=\"\",D199=\"\"),\"\",D199-C199+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C200=\"\",\"\",C200)","v":0},{"$f":"IF(OR(C200=\"\",D200=\"\"),\"\",D200-C200+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C201=\"\",\"\",C201)","v":0},{"$f":"IF(OR(C201=\"\",D201=\"\"),\"\",D201-C201+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C202=\"\",\"\",C202)","v":0},{"$f":"IF(OR(C202=\"\",D202=\"\"),\"\",D202-C202+1)","v":0}]
[{"$nulls":5},{"$f":"IF(C203=\"\",\"\",C203)","v":0},{"$f":"IF(OR(C203=\"\",D203=\"\"),\"\",D203-C203+1)","v":0}]

{"sheet":"RACI","index":8,"n_rows":7,"n_cols":12,"rows_kept":7}
["Matrice RACI"]
[]
["Objet","Rôle 1","Rôle 2","Rôle 3","Rôle 4","Rôle 5","Rôle1","Rôle2","Rôle3","Rôle4","Rôle5","Client"]
["PQP","Resp Qualité","Méthodes","Prod","HSE","Client","R","A","C","I","I","C"]
["Procédures Traçabilité","Méthodes","Resp Qualité","Prod","HSE","Client","A","C","C","I","I","I"]
["Plan de Contrôle","Méthodes","Resp Qualité","Prod","HSE","Client","A","C","R","I","I","C"]
["Essais FPY","Prod","Resp Qualité","Méthodes","HSE","Client","R","I","C","I","I","I"]

{"sheet":"Communication","index":9,"n_rows":7,"n_cols":7,"rows_kept":7}
["Plan de Communication (Flux d'information)"]
[]
["Rituel","Fréquence","Durée","Participants","Canal","Contenu","Animateur"]
["Daily QSE","Quotidien","15 min","Équipe projet","Teams/Visuel poste","Points chauds, actions J+1","Resp Qualité"]
["Revue Hebdo","Hebdomadaire","30 min","Chefs de service","Salle/Teams","KPIs, Pareto, blocages, décisions","Chef Projet"]
["Revue Client","Mensuel","60 min","Client + Core Team","Teams","Avancement, risques, écarts, actions","Chef Projet"]
["Revue Direction","Mensuel","45 min","Direction","Salle","Indicateurs clés, arbitrages","Directeur Site"]

{"sheet":"KPI_Dashboard","index":10,"n_rows":12,"n_cols":6,"rows_kept":12}
["KPI Projet — Tableau de bord"]
[]
["Zone de calcul (ne pas supprimer)","Valeur",null,null,"Cartes KPI"]
[{"$nulls":4},"Couverture exigences",{"$f":"B8","v":{"v":0,"d":"0.0%"}}]
["Indicateur","Valeur","Formule (info)",null,"Essais OK",{"$f":"B9","v":{"v":0,"d":"0.0%"}}]
["Total exigences",{"$f":"COUNTA(tblReq[ID Exigence])","v":0},null,null,"On-time livrables",{"$f":"B10","v":{"v":0,"d":"0.0%"}}]
["Exigences avec descendance",{"$f":"SUM(tblFlow[FirstOccur])","v":0},null,null,"Actions en retard",{"$f":"B11","v":0}]
["Couverture exigences (%)",{"$f":"IF(B6=0,\"\",B7/B6)","v":{"v":0,"d":"0.0%"}}]
["Taux essais OK (%)",{"$f":"IF(COUNTA(tblTests[Résultat])=0,\"\",COUNTIF(tblTests[Résultat],\"OK\")/COUNTA(tblTests[Résultat]))","v":{"v":0,"d":"0.0%"}}]
["Livrables à l'heure (%)",{"$f":"IF(COUNTIF(tblWBS[Statut],\"Livré\")=0,\"\",COUNTIFS(tblWBS[Statut],\"Livré\",tblWBS[Date réelle],\"<=\"&tblWBS[Date prévue])/COUNTIF(tblWBS[Statut],\"Livré\"))","v":{"v":0,"d":"0.0%"}}]
["Actions en retard (#)",{"$f":"COUNTIFS(tblActions[Statut],\"Ouverte\",tblActions[Échéance],\"<\"&TODAY())","v":0}]
["% actions clôturées < 30 j",{"$f":"IF(COUNTIF(tblActions[Statut],\"Clôturée\")=0,\"\",SUMPRODUCT((tblActions[Statut]=\"Clôturée\")*(IFERROR(tblActions[Date clôture]-tblActions[Échéance],0)<=30))/COUNTIF(tblActions[Statut],\"Clôturée\"))","v":{"v":0,"d":"0.0%"}}]