## Instructions
Team Resource Planning Template
How to use
1. Update the week start date and planning thresholds in Parameters.
2. Add or edit team members in Team_Resources.
3. Enter projects and tasks in Project_Planner.
4. Review weekly workload and utilisation in Weekly_View.
5. Use Dashboard for capacity, risk, team mix, and task status.

## Parameters
Planning Controls
Selected Week Start | 2026-03-16 | Update this date to shift weekly summaries automatically.
Work Days per Week | 5 | Typical UK work pattern.
Standard Hours per Day | 8 | Used as base capacity.
Default Utilisation | 0.9 | Represents realistic productive availability.
Warning Threshold | 1 | Above this level, the file flags a resource as At Risk.
Stretch Threshold | 1.15 | Above this level, the file flags a resource as Overloaded.
Selected Week End |  | Calculated from selected week start and work days.

## Lists
Validation Lists
Role | Department | Priority | Status | Billable | Team
Business Analyst | Customer Success | High | Not Started | Yes | Birmingham Ops
Customer Success Lead | Design | Medium | In Progress | No | Client Solutions
Data Analyst | Engineering | Low | Blocked |  | London Delivery
DevOps Engineer | Finance |  | Completed |  | Manchester Engineering
Finance Analyst | HR |  |  |  | Shared Services
HR Partner | Operations
Maintenance Planner | Procurement
Process Engineer | Quality
Procurement Specialist | Support
Product Designer | Technology
Programme Manager
Project Coordinator
QA Specialist
Service Desk Manager
Software Developer

## Team_Resources
UK Resource Pool
Resource ID | Name | Role | Department | Team | FTE | Std Hours/Day | Utilisation | Leave Days | Available Days | Weekly Capacity Hrs | Cost Rate | Notes
R001 | Oliver Bennett | Programme Manager | Operations | London Delivery | 1 | 8 | 90% | 0 |  |  | 55 | Portfolio lead
R002 | Amelia Clarke | Process Engineer | Engineering | Manchester Engineering | 1 | 8 | 92% | 1 |  |  | 52 | Capacity modelling
R003 | George Harris | Product Designer | Design | London Delivery | 1 | 8 | 85% | 0 |  |  | 46 | UX and service design
R004 | Emily Turner | Software Developer | Technology | Manchester Engineering | 1 | 8 | 95% | 0 |  |  | 58 | Back-end build
R005 | Jack Wilson | Finance Analyst | Finance | Shared Services | 0.8 | 8 | 88% | 0 |  |  | 42 | Reporting and controls
R006 | Sophie Mitchell | Project Coordinator | Operations | Birmingham Ops | 1 | 8 | 86% | 0 |  |  | 44 | PMO support
R007 | Harry Thompson | QA Specialist | Quality | Birmingham Ops | 1 | 8 | 90% | 0 |  |  | 47 | Testing and QA
R008 | Isla Roberts | Data Analyst | Technology | Shared Services | 1 | 8 | 93% | 1 |  |  | 49 | BI and dashboards
R009 | Thomas Walker | HR Partner | HR | Shared Services | 0.8 | 8 | 82% | 0 |  |  | 40 | Recruitment support
R010 | Charlotte Hughes | Customer Success Lead | Customer Success | Client Solutions | 1 | 8 | 87% | 0 |  |  | 48 | Client onboarding
R011 | Noah Cooper | Maintenance Planner | Operations | Birmingham Ops | 1 | 8 | 91% | 0 |  |  | 51 | Asset readiness
R012 | Mia Edwards | Business Analyst | Operations | London Delivery | 1 | 8 | 89% | 0 |  |  | 50 | Requirements and process mapping
R013 | Leo Richardson | DevOps Engineer | Technology | Manchester Engineering | 1 | 8 | 94% | 0 |  |  | 60 | Release support
R014 | Evie Collins | Procurement Specialist | Procurement | Shared Services | 1 | 8 | 84% | 0 |  |  | 43 | Supplier coordination
R015 | Arthur Morgan | Service Desk Manager | Support | Client Solutions | 1 | 8 | 88% | 0 |  |  | 46 | Support operations
TOTAL

## Project_Planner
Project Planner
Task ID | Project | Task Name | Resource ID | Resource Name | Priority | Status | Start Date | End Date | Duration Days | Planned Hours | Hours/Day | Overlap Days | Week Assigned Hrs | % Complete | Billable | Comments
T001 | Warehouse Upgrade | Weekly governance review | R001 |  | High | In Progress | 2026-03-16 | 2026-03-20 |  | 10 |  |  |  | 65% | Yes | Steering cadence
T002 | Warehouse Upgrade | Flow analysis and line balancing | R002 |  | High | In Progress | 2026-03-16 | 2026-03-20 |  | 28 |  |  |  | 50% | Yes | Ops engineering
T003 | Client Portal Refresh | Wireframes and user journeys | R003 |  | Medium | In Progress | 2026-03-16 | 2026-03-19 |  | 18 |  |  |  | 55% | Yes | Initial sprint
T004 | Client Portal Refresh | API integration sprint 1 | R004 |  | High | In Progress | 2026-03-17 | 2026-03-23 |  | 34 |  |  |  | 30% | Yes | Milestone build
T005 | March Reporting Pack | Finance dashboard consolidation | R005 |  | Medium | In Progress | 2026-03-18 | 2026-03-22 |  | 16 |  |  |  | 40% | No | Board pack support
T006 | CRM Migration | Training schedule coordination | R006 |  | Medium | Not Started | 2026-03-17 | 2026-03-21 |  | 20 |  |  |  | 10% | Yes | Training slots
T007 | ISO 9001 Review | Test script execution | R007 |  | High | In Progress | 2026-03-16 | 2026-03-20 |  | 24 |  |  |  | 35% | Yes | QA cycle
T008 | Data Warehouse | KPI dataset preparation | R008 |  | High | In Progress | 2026-03-16 | 2026-03-21 |  | 26 |  |  |  | 45% | Yes | Dashboard feed
T009 | Q2 Hiring Plan | Interview scheduling and offers | R009 |  | Medium | In Progress | 2026-03-18 | 2026-03-24 |  | 22 |  |  |  | 25% | No | Hiring coordination
T010 | Client Onboarding | Priority account mobilisation | R010 |  | High | In Progress | 2026-03-16 | 2026-03-19 |  | 18 |  |  |  | 60% | Yes | Client launch
T011 | Planned Shutdown | Maintenance readiness review | R011 |  | High | Not Started | 2026-03-19 | 2026-03-25 |  | 24 |  |  |  | 10% | Yes | Shutdown prep
T012 | Process Optimisation | Requirements workshops | R012 |  | Medium | In Progress | 2026-03-16 | 2026-03-20 |  | 20 |  |  |  | 50% | Yes | Lean workshops
T013 | Release Management | CI/CD pipeline hardening | R013 |  | High | In Progress | 2026-03-16 | 2026-03-22 |  | 30 |  |  |  | 40% | Yes | Release control
T014 | Supplier Review | Contract pack preparation | R014 |  | Low | Not Started | 2026-03-18 | 2026-03-24 |  | 14 |  |  |  | 5% | No | Renewal file
T015 | Service Improvement | Incident backlog triage | R015 |  | High | In Progress | 2026-03-16 | 2026-03-18 |  | 15 |  |  |  | 70% | Yes | Backlog reduction
T016 | Warehouse Upgrade | Costed implementation options | R012 |  | Medium | Not Started | 2026-03-20 | 2026-03-24 |  | 12 |  |  |  | 0% | Yes | Decision paper
T017 | Client Portal Refresh | Regression testing | R007 |  | Medium | Not Started | 2026-03-21 | 2026-03-26 |  | 18 |  |  |  | 0% | Yes | Pre-release QA
T018 | CRM Migration | Configuration changes | R004 |  | High | Not Started | 2026-03-21 | 2026-03-27 |  | 22 |  |  |  | 0% | Yes | Sprint follow-up
T019 | March Reporting Pack | Variance commentary drafting | R005 |  | Medium | Not Started | 2026-03-23 | 2026-03-26 |  | 10 |  |  |  | 0% | No | Month-end notes
T020 | Data Warehouse | Executive dashboard design | R003 |  | Medium | In Progress | 2026-03-18 | 2026-03-24 |  | 16 |  |  |  | 20% | Yes | Visual concepts
T021 | Q2 Hiring Plan | Hiring manager calibration | R009 |  | Low | Not Started | 2026-03-23 | 2026-03-25 |  | 8 |  |  |  | 0% | No | Interview standards
T022 | Supplier Review | Vendor scorecard analysis | R014 |  | Medium | In Progress | 2026-03-16 | 2026-03-19 |  | 14 |  |  |  | 50% | No | Procurement analysis
T023 | Service Improvement | Knowledge base refresh | R015 |  | Medium | In Progress | 2026-03-17 | 2026-03-21 |  | 12 |  |  |  | 30% | Yes | Support content
T024 | Client Onboarding | Implementation risk review | R010 |  | High | Not Started | 2026-03-20 | 2026-03-24 |  | 10 |  |  |  | 0% | Yes | Risk workshop
T025 | Release Management | Environment cutover checklist | R013 |  | High | Not Started | 2026-03-23 | 2026-03-27 |  | 16 |  |  |  | 0% | Yes | Go-live prep
T026 | Planned Shutdown | Spare parts readiness | R011 |  | Medium | In Progress | 2026-03-16 | 2026-03-20 |  | 18 |  |  |  | 40% | Yes | Critical materials
T027 | Process Optimisation | Current state mapping | R002 |  | Medium | In Progress | 2026-03-18 | 2026-03-24 |  | 20 |  |  |  | 20% | Yes | Workflow analysis
T028 | CRM Migration | Comms plan and FAQ | R006 |  | Low | In Progress | 2026-03-16 | 2026-03-18 |  | 9 |  |  |  | 75% | No | Change management

## Weekly_View
Weekly Resource Summary
Week Start
Week End
Resource ID | Name | Role | Department | Team | Weekly Capacity | Assigned Hours | Remaining Hours | Utilisation % | Load Status

## Dashboard
Team Resource Planning Dashboard - UK Localised Sample
Total Weekly Capacity |  |  | Assigned Hours |  |  | Remaining Hours |  |  | Overall Utilisation
Resource | Capacity | Assigned | Utilisation |  | Team | Capacity | Assigned | Utilisation |  | Load Status | Count
[5 empty] | Birmingham Ops |  |  |  |  | Balanced
[5 empty] | Client Solutions |  |  |  |  | At Risk
[5 empty] | London Delivery |  |  |  |  | Overloaded
Manchester Engineering
Shared Services
[10 empty] | Task Status | Count
Not Started
In Progress
Blocked
Completed
Top Priority Tasks This Week
Task | Project | Resource | Assigned Hrs | Status
Weekly governance review | Warehouse Upgrade |  |  | In Progress
Flow analysis and line balancing | Warehouse Upgrade |  |  | In Progress
API integration sprint 1 | Client Portal Refresh |  |  | In Progress
Test script execution | ISO 9001 Review |  |  | In Progress
KPI dataset preparation | Data Warehouse |  |  | In Progress
Priority account mobilisation | Client Onboarding |  |  | In Progress
Maintenance readiness review | Planned Shutdown |  |  | Not Started
CI/CD pipeline hardening | Release Management |  |  | In Progress