## UK renovation budget
UK Home Renovation Budget Calculator
One-page Excel calculator to estimate renovation costs, compare planned and actual spend, and monitor variances by work package.
Project assumptions |  |  |  | Theoretical budget |  | Planned budget |  | Actual spend | Overall variance
Renovated area (m²) | 85
Target cost per m² | 1500
Contingency allowance | 12% |  |  | Contingency |  | Estimated taxes |  | Total project budget | Actual cost per m²
Estimated VAT / taxes | 20%
Work package | Priority | Planned budget | Actual | Variance | Progress | Status | Comment | UK reference rates
Strip-out / waste removal | High | 5500 | 5200 |  | 100% | Completed | Skip hire and clearance included | Light refresh: around £700–£1,200 / m² for redecorating, flooring and minor upgrades.
Structural works | High | 18000 | 19200 |  | 70% | In progress | Structural opening and supports
Roofing / waterproofing | High | 9000 | 8400 |  | 60% | In progress | Allowance based on repair scope | Standard renovation: around £1,200–£1,800 / m² for broader refurbishment and updated services.
Electrical rewiring | High | 8500 | 9100 |  | 45% | In progress | Consumer unit and full rewire
Plumbing / heating | High | 9000 | 8700 |  | 40% | In progress | Boiler and radiator allowance | Full refurbishment: around £1,800–£2,500 / m². London or high-end projects can reach roughly £2,500–£3,500 / m².
Insulation / energy upgrades | Medium | 8500 | 0 |  | 10% | To start | Walls, loft or floor insulation
Windows and external doors | Medium | 12000 | 0 |  | 0% | To start | Double glazing allowance
Flooring | Medium | 6500 | 0 |  | 0% | To start | Materials and fitting
Plastering and painting | Low | 7000 | 0 |  | 0% | To start | Internal finish allowance
Kitchen | Medium | 15000 | 0 |  | 0% | To start | Mid-range kitchen allowance
Bathroom | High | 9000 | 0 |  | 0% | To start | Bathroom renovation allowance
Professional fees | Medium | 5000 | 5000 |  | 100% | Completed | Surveyor / architect / planning
Contingency reserve | High | 12000 | 1500 |  | 20% | In progress | Reserve for hidden issues
Note on C8: Reference benchmarks compiled from UK renovation cost guides: https://energy.ecoflow.com/uk/blog/home-renovation-cost https://www.checkatrade.com/blog/cost-guides/cost-renovating-house/ https://bhstudio.co.uk/blog/home-renovation-cost-london-2026
Note on C9: Reference benchmarks compiled from UK renovation cost guides: https://energy.ecoflow.com/uk/blog/home-renovation-cost https://www.checkatrade.com/blog/cost-guides/cost-renovating-house/ https://bhstudio.co.uk/blog/home-renovation-cost-london-2026
Note on K15: Reference benchmarks compiled from UK renovation cost guides: https://energy.ecoflow.com/uk/blog/home-renovation-cost https://www.checkatrade.com/blog/cost-guides/cost-renovating-house/ https://bhstudio.co.uk/blog/home-renovation-cost-london-2026
Note on K17: Reference benchmarks compiled from UK renovation cost guides: https://energy.ecoflow.com/uk/blog/home-renovation-cost https://www.checkatrade.com/blog/cost-guides/cost-renovating-house/ https://bhstudio.co.uk/blog/home-renovation-cost-london-2026
Note on K19: Reference benchmarks compiled from UK renovation cost guides: https://energy.ecoflow.com/uk/blog/home-renovation-cost https://www.checkatrade.com/blog/cost-guides/cost-renovating-house/ https://bhstudio.co.uk/blog/home-renovation-cost-london-2026

## Sources
UK renovation benchmark sources
Benchmark | Indicative range | Use in workbook | Source URL
UK renovation cost per m² | £1,000–£2,500 / m² | Target cost per m² and rate panel | https://energy.ecoflow.com/uk/blog/home-renovation-cost
UK 3-bedroom renovation cost | £43,530–£110,350 + 10–15% contingency | Contingency guidance | https://www.checkatrade.com/blog/cost-guides/cost-renovating-house/
London renovation cost per m² | £800–£3,500 / m² depending on scope and finish | High-end / London benchmark | https://bhstudio.co.uk/blog/home-renovation-cost-london-2026