## Advanced Risk Register
ADVANCED DYNAMIC RISK REGISTER
RISK IDENTIFICATION | [5 empty] | AUTOMATED SCORING | [5 empty] | MITIGATION TRACKING | [5 empty] | GOVERNANCE & REVIEW
Risk ID | Risk Title | Category | Department | Owner | Probability | Impact | Inherent Score | Priority | Control Effectiveness | Residual Score | Residual Level | Mitigation Action | Action Owner | Due Date | Status | Last Review | Trend | Escalation | Business Impact | Likelihood Comment | Residual Exposure | Review Frequency | Executive Notes
R001 | Cybersecurity Breach | Cybersecurity | IT | Robert | 5 | 4 |  |  | Weak |  |  | Deploy MFA | James | 2026-06-15 | Open | 2026-05-20 | ↑ | Critical | Severe operational disruption | External threat activity | High | Monthly | Board escalation required
R002 | Supplier Delay | Operational | Supply | Mary | 4 | 4 |  |  | Partial |  |  | Diversify suppliers | Laura | 2026-06-30 | Open | 2026-05-18 | → | High | Production interruption | Single supplier dependency | Medium | Monthly | Monitor logistics exposure
R003 | Compliance Failure | Compliance | Legal | Trevor | 3 | 4 |  |  | Strong |  |  | Internal audit | Emma | 2026-06-10 | Controlled | 2026-05-16 | ↓ | Medium | Regulatory penalty | Documentation inconsistency | Low | Quarterly | Stable control environment
R004 | Financial Fraud | Financial | Finance | Anna | 5 | 5 |  |  | Weak |  |  | Strengthen approval controls | Daniel | 2026-06-05 | Open | 2026-05-22 | ↑ | Critical | Financial losses | Suspicious transactions | Critical | Weekly | Executive supervision active
R005 | Infrastructure Failure | IT | Infrastructure | James | 4 | 3 |  |  | Partial |  |  | Preventive maintenance | Sophie | 2026-07-01 | In Progress | 2026-05-14 | → | High | Service interruption | Recurring outages | Medium | Monthly | Requires infrastructure investment